## Lists
Status | Priority | Owner Role | Cadence
Not Started | Critical | Executive Sponsor | Daily
In Progress | High | Project Manager | Twice Weekly
Blocked | Medium | Project Controls Lead | Weekly
Complete | Low | Design Manager | Monthly
Deferred |  | Change Manager | Quarterly
Data Analyst

## KPI_Targets
KPI Baselines, Targets, and Control Limits
Targets are case-study management objectives, not universal construction-industry standards.
KPI ID | KPI | Baseline | 90-Day Target | 180-Day Target | Direction | Yellow Limit | Red Limit | Owner | Measurement
KPI-01 | RFI on-time rate | 45.68% | 70% | 80% | Higher | 60% | 50% | Design Manager | Weekly
KPI-02 | Average RFI response days | 12.21 | 10 | 8 | Lower | 12 | 15 | Design Manager | Weekly
KPI-03 | Average change approval days | 28.91 | 24 | 20 | Lower | 28 | 35 | Change Manager | Weekly
KPI-04 | Pending change exposure | 88104000 | 66078000 | 52862400 | Lower | 74888400 | 88104000 | Change Manager | Weekly
KPI-05 | Overdue open RFIs | 295 | 148 | 75 | Lower | 220 | 295 | Design Manager | Twice Weekly
KPI-06 | Forecast incorporation lag days | 6.58 | 5 | 3 | Lower | 7 | 10 | Project Controls Lead | Weekly
KPI-07 | Old pending changes >35 days | 219 | 131 | 88 | Lower | 175 | 219 | Change Manager | Weekly
KPI-08 | Approved changes not incorporated | 56 | 10 | 0 | Lower | 25 | 56 | Project Controls Lead | Weekly
KPI-09 | Red projects | 29 | 18 | 10 | Lower | 23 | 29 | Executive Sponsor | Weekly
KPI-10 | Green projects | 13 | 22 | 30 | Higher | 18 | 13 | Executive Sponsor | Weekly
KPI-11 | Top-10 project action closure rate | 0% | 75% | 90% | Higher | 0.5 | 0.25 | Project Manager | Weekly
KPI-12 | Revision-loop reduction in flagged projects | 0% | 20% | 35% | Higher | 0.1 | 0 | Design Manager | Monthly

## Executive_Summary
Construction Change Order and RFI Analytics — Act Plan
Management operating plan for workflow recovery, accountability, governance, KPI targets, and continuous improvement. All projects and records are synthetic.
45.68% |  |  | 70% |  |  | 28.91 | 24
Current RFI On-Time |  |  | 90-Day RFI Target |  |  | Current Approval Cycle | 90-Day Approval Target
88104000 |  |  | 66078000 |  |  | 29 | 18
Current Pending Exposure |  |  | 90-Day Exposure Target |  |  | Current Red Projects | 90-Day Red Target
Action Portfolio | Total | Complete | In Progress | Blocked | Completion %
Act actions | 16 | 0 | 0 | 0 | 0%
Priority Outcomes | 30 Days | 60 Days | 90 Days | Owner | Success Evidence
Stabilize critical RFI backlog | All High/Critical overdue items assigned | Backlog trend declining | No High/Critical RFI >7 days | Design Manager | Exception report
Reduce pending commercial exposure | Top 10 project reviews launched | Old pending changes reduced | Pending exposure ≤$66.1M | Change Manager | Change aging report
Improve decision cycle | Weekly decision board active | Average cycle ≤26 days | Average cycle ≤24 days | Project Controls Lead | Cycle-time trend
Restore forecast discipline | Approved items reconciled | Lag ≤6 days | Lag ≤5 days; ≤10 missing | Project Controls Lead | Forecast reconciliation
Improve workflow health | 29 Red projects baselined | Red projects ≤23 | Red projects ≤18 | Executive Sponsor | Health dashboard
Lifecycle terminology: Act aligns with Deployment in CRISP-DM; Improve and Control in DMAIC; Deployment and Customer Acceptance in Microsoft's data-science lifecycle; and Executing, Monitoring and Controlling, transition, and Closing in PMI governance terminology.

## 30_60_90_Roadmap
30/60/90-Day Implementation Roadmap
Sequenced implementation from stabilization to control and continuous improvement.
Window | Objective | Key Activities | Primary Owner | Deliverable | Decision Gate | Dependencies | Success Measure
Days 0–30 | Stabilize exceptions | Launch top-10 project triage; assign all High/Critical overdue RFIs; validate old pending changes; reconcile approved changes not incorporated; establish weekly boards. | Project Controls Lead | Validated exception register | Executive sponsor approves priorities | Accurate project ownership and current status | 100% top-10 projects reviewed
Days 0–30 | Establish governance | Publish RFI response standards; create change approval calendar; define escalation matrix; confirm dashboard owners. | Executive Sponsor | Governance charter | Owners accept responsibilities | Leadership participation | All recurring meetings active
Days 31–60 | Reduce backlog | Run discipline backlog sprints; close invalid or obsolete items; negotiate oldest pending changes; track forecast incorporation. | Design Manager / Change Manager | Backlog reduction report | Trend must improve for two consecutive weeks | Timely decisions and pricing | Overdue RFIs and old pending changes declining
Days 31–60 | Improve workflow quality | Introduce RFI submission quality checklist; commercial package completeness gate; track revision loops by project and discipline. | Design Manager | Quality-gate checklist | Pilot projects meet adoption target | Training and templates | Revision loops reduced in pilot
Days 31–60 | Pilot digital coordination | Select Low digital-coordination projects; use model coordination and structured issue review before RFI submission. | Design Manager | Pilot evaluation | Continue only if cycle time improves | BIM/design-team participation | Pilot response time improves
Days 61–90 | Standardize control | Embed KPI targets into weekly project-controls reporting; automate alerts; add executive exception narrative. | Project Controls Lead | Controlled reporting package | Executive acceptance | Stable data refresh | KPI package issued on schedule
Days 61–90 | Close management gaps | Complete corrective actions for priority projects; confirm owners, residual risks, and unresolved decisions. | Project Manager | Priority-project closure report | Residual risks accepted or escalated | Owner and design decisions | ≥75% top-10 action closure
Days 61–90 | Benefits review | Compare baseline to 90-day targets; document benefits, limitations, and next-quarter priorities. | Data Analyst | Benefits realization report | Approve next-quarter plan | Reliable metric history | Target gaps quantified
Days 91–180 | Sustain and optimize | Continue monthly root-cause reviews; expand successful pilots; recalibrate thresholds where justified. | Executive Sponsor | Continuous-improvement backlog | Quarterly governance review | Sufficient history | 180-day targets tracked

## Action_Register
Management Action Register
The register assigns owners, implementation windows, evidence, and measurable success criteria.
Action ID | Workstream | Action | Business Rationale | Priority | Owner | Start Window | Due Window | Evidence | KPI Link | Status | Notes
ACT-001 | Project triage | Conduct structured review of all 29 Red projects, beginning with the top 10 priority projects. | Risk is concentrated and requires project-specific validation. | Critical | Project Controls Lead | Day 1 | Day 15 | Signed review record | KPI-09 | Not Started
ACT-002 | RFI backlog | Assign and escalate every High/Critical overdue RFI; no item may remain unowned. | Overdue critical decisions can delay field work and create downstream changes. | Critical | Design Manager | Day 1 | Day 10 | Exception register | KPI-05 | Not Started
ACT-003 | RFI standards | Adopt response standards: Critical 3 days, High 5 days, Medium 10 days, Low 14 days. | Current on-time rate is 45.7%. | High | Design Manager | Day 1 | Day 20 | Published service-level standard | KPI-01; KPI-02 | Not Started
ACT-004 | Change aging | Create a weekly aging board for all Submitted, Under Review, and Pending changes. | Pending exposure is $88.10M and 219 changes are older than 35 days. | Critical | Change Manager | Day 1 | Day 7 | Weekly aging report | KPI-04; KPI-07 | Not Started
ACT-005 | Decision calendar | Reserve recurring owner-decision sessions with required approvers and pre-read deadlines. | Slow decision profiles underperform in both workflows. | High | Executive Sponsor | Day 1 | Day 14 | Standing calendar | KPI-03 | Not Started
ACT-006 | Forecast incorporation | Reconcile all approved changes and incorporate them into project forecasts within five business days. | 56 approved changes were not observed as incorporated. | Critical | Project Controls Lead | Day 1 | Day 30 | Forecast reconciliation log | KPI-06; KPI-08 | Not Started
ACT-007 | RFI quality gate | Require scope, location, drawing references, impact statement, and proposed response path before submission. | Revision loops are associated with longer response cycles. | High | Design Manager | Day 15 | Day 45 | RFI checklist and audit | KPI-12 | Not Started
ACT-008 | Change package gate | Require scope narrative, cost breakdown, schedule analysis, supporting RFI, and authority before approval review. | Incomplete packages create returns and approval delay. | High | Change Manager | Day 15 | Day 45 | Commercial completeness checklist | KPI-03; KPI-12 | Not Started
ACT-009 | Coordination conflict review | Run monthly Pareto review of coordination conflicts and assign prevention actions by discipline. | Coordination Conflict generated the greatest RFI cost impact. | High | Design Manager | Day 20 | Day 60 | Pareto and prevention log | KPI-02 | Not Started
ACT-010 | Digital coordination pilot | Pilot structured model coordination on selected Low digital-coordination projects. | High digital coordination is associated with stronger RFI response performance. | Medium | Design Manager | Day 30 | Day 75 | Pilot result report | KPI-01; KPI-02 | Not Started
ACT-011 | Project action plans | Create tailored recovery plans for each top-10 priority project. | Portfolio scoring identifies concentrated multi-indicator exposure. | Critical | Project Manager | Day 1 | Day 21 | Project recovery plans | KPI-11 | Not Started
ACT-012 | Workflow alerts | Generate automated exception files for Red projects, overdue RFIs, old pending changes, and forecast-incorporation gaps. | Manual review is slower and less consistent. | High | Data Analyst | Day 30 | Day 75 | Automated alert output | KPI-05; KPI-07; KPI-08; KPI-09 | Not Started
ACT-013 | Executive dashboard | Issue a weekly executive exception dashboard with decisions required and owner commitments. | Executives need concise decision-focused communication. | High | Project Controls Lead | Day 15 | Day 45 | Published dashboard | KPI-01–KPI-11 | Not Started
ACT-014 | Benefits tracking | Measure actual reduction in response time, approval cycle, backlog, exposure, and Red-project count. | Benefits must be demonstrated rather than assumed. | High | Data Analyst | Day 30 | Day 90 | Benefits realization report | KPI-01–KPI-12 | Not Started
ACT-015 | Threshold review | Review thresholds quarterly and recalibrate only with documented evidence and stakeholder approval. | Thresholds are case-study assumptions, not universal standards. | Medium | Project Controls Lead | Day 75 | Day 90 | Threshold decision log | KPI-01–KPI-12 | Not Started
ACT-016 | Model governance | Do not deploy the exploratory RFI-to-change model; collect better temporal data and define a governed pilot. | Submission-only AUC was 0.510 and diagnostic AUC was 0.631. | Critical | Data Analyst | Day 1 | Day 90 | Model governance memo | None | Not Started

## Governance_Cadence
Governance Cadence and Decision Rights
Meetings must produce decisions, accountable owners, due dates, and documented escalation.
Forum | Cadence | Chair | Required Participants | Purpose | Inputs | Outputs | Escalation Trigger | Timebox
Exception check | Daily | Project Controls Lead | Project controls, design, change management | Review newly Red exceptions and missed commitments. | Automated alert file | Assigned owner and due date | Critical RFI >3 days overdue; unowned Red action | 15 min
RFI coordination huddle | Twice Weekly | Design Manager | Architect, engineers, contractor, CM | Resolve High/Critical RFIs and discipline bottlenecks. | RFI aging and priority list | Responses, escalations, coordination actions | High/Critical RFI >7 days overdue | 30 min
Change review board | Weekly | Change Manager | Owner rep, PM, cost, scheduler, designer | Decide old and high-value pending changes. | Change aging, pricing package, schedule analysis | Approve, reject, revise, or escalate | Pending >35 days or exposure >1.5% budget | 60 min
Project workflow review | Weekly | Project Controls Lead | PMs for Red/Yellow projects | Review project score, actions, and commitments. | Health dashboard, top-10 list | Updated recovery actions | Risk score ≥6 or repeated missed commitment | 45 min
Forecast reconciliation | Weekly | Project Controls Lead | Cost manager, change manager, PM | Ensure approved changes are reflected in forecasts. | Approval register and forecast | Reconciled forecast log | Approved item not incorporated >5 business days | 30 min
Executive steering review | Monthly | Executive Sponsor | Functional leads and priority PMs | Review portfolio targets, unresolved decisions, and benefits. | Executive dashboard and benefits tracker | Executive decisions and resource allocation | 90-day target off trajectory | 60 min
Root-cause review | Monthly | Design Manager | Design disciplines, CM, data analyst | Review Pareto of RFI types, disciplines, and revision loops. | RFI type and discipline analysis | Prevention actions | Repeated cause in top three for two months | 45 min
Methods and threshold review | Quarterly | Project Controls Lead | Executive sponsor, data analyst, PM leaders | Review metric definitions, thresholds, and analytical validity. | Metric history and exceptions | Approved methodology changes | Material drift or governance issue | 90 min

## Top_10_Project_Actions
Top 10 Priority Project Action Plans
Project-specific starting actions generated from the validated transparent risk indicators.
Rank | Project ID | Project | Risk Score | Health | Avg RFI Days | Avg Approval Days | Pending / Budget | Primary Trigger | Immediate Action | Owner | Due Window | Status | Success Evidence
1 | PRJ-006 | Summit Corporate Center | 10 | Red | 11.4848 | 32.5 | 2.658% | High/Critical overdue, Pending exposure, Forecast lag | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
2 | PRJ-025 | Canyon Transit-Oriented Development | 9 | Red | 17.0323 | 51 | 2.95% | RFI response, Approval cycle, Pending exposure | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
3 | PRJ-075 | Summit Urban Village | 9 | Red | 18.5833 | 43.625 | 1.403% | RFI response, High/Critical overdue, Approval cycle | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
4 | PRJ-051 | Evergreen Apartments | 9 | Red | 21.0962 | 45.8571 | 0.562% | RFI response, High/Critical overdue, Approval cycle | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
5 | PRJ-013 | Aspen Civic Complex 2 | 9 | Red | 10.3947 | 29.5714 | 0.515% | High/Critical overdue, Not incorporated | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
6 | PRJ-016 | Evergreen Town Center | 8 | Red | 17.025 | 35.6 | 1.834% | RFI response, Approval cycle, Pending exposure | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
7 | PRJ-039 | Silver Creek Urban Village 2 | 8 | Red | 12.3077 | 39.3333 | 1.401% | Approval cycle, Not incorporated | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
8 | PRJ-019 | Pioneer Research Center | 8 | Red | 14.9423 | 35.8 | 1.26% | High/Critical overdue, Approval cycle | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
9 | PRJ-017 | Mountain Gate Transit Center | 8 | Red | 19.0392 | 33.2 | 0.831% | RFI response | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed
10 | PRJ-021 | Desert View Processing Plant | 8 | Red | 18 | 36.4545 | 0.172% | RFI response, Approval cycle, Forecast lag | Launch executive recovery review; assign owners to all Red triggers; close High/Critical overdue RFIs; decide oldest pending changes; reconcile forecast. | Project Manager | Day 21 | Not Started | Risk score reduced and overdue commitments closed

## Control_Standards
Proposed Workflow Control Standards
Proposed operating standards derived from the portfolio analysis and intended for management validation.
Control ID | Control | Standard | Owner | Evidence | Exception | Escalation | Review Frequency
CTL-001 | RFI required response | Critical 3 days; High 5; Medium 10; Low 14. | Design Manager | RFI log | Required date missed | Escalate by priority and age | Twice Weekly
CTL-002 | RFI submission completeness | Location, drawing reference, scope question, impact, and required decision must be complete. | Design Manager | Checklist audit | Missing required field | Return before workflow start | Monthly
CTL-003 | Change package completeness | Scope narrative, cost detail, schedule analysis, supporting documents, authority, and requested decision. | Change Manager | Package checklist | Incomplete package | Return with deficiencies documented | Weekly
CTL-004 | Change decision aging | All pending items reviewed weekly; items >35 days require executive disposition plan. | Change Manager | Aging report | Pending >35 days | Executive sponsor review | Weekly
CTL-005 | Forecast incorporation | Approved changes incorporated within five business days. | Project Controls Lead | Reconciliation log | Lag >5 days | Escalate to PM and cost lead | Weekly
CTL-006 | Project health recovery | Red projects require a documented action plan and weekly status until score <6. | Project Manager | Recovery plan | Score ≥6 | Executive steering review | Weekly
CTL-007 | Revision-loop review | Repeated return loops require root-cause classification and prevention action. | Design Manager | Revision-loop report | Two or more returns | Monthly root-cause forum | Monthly
CTL-008 | Analytical model governance | Exploratory model may not drive production decisions without formal validation. | Data Analyst | Model governance memo | Unauthorized model use | Stop use and notify sponsor | Quarterly
CTL-009 | Data quality | Dashboard refresh requires primary-key, foreign-key, row-reconciliation, and formula-error checks. | Data Analyst | Validation report | Any failed critical check | Do not publish refresh | Each Refresh

## Automation_Alerts
Automation and Alert Plan
The alert design is implementation-ready but does not create a live scheduled service by itself.
Alert ID | Condition | Frequency | Audience | Source | Output | Severity | Suppression / Deduplication | Action
ALT-001 | Project Workflow_Health = Red | Daily | Executive sponsor, controls lead, PM | project_workflow_risk_summary.csv | Red project alert | Critical | One alert per project per day unless score worsens | Open or update recovery plan
ALT-002 | High/Critical RFI is overdue >7 days | Daily | Design manager, PM | rfi_log_clean.csv | RFI escalation alert | Critical | Suppress after owner and due date are confirmed for 24 hours | Obtain response or executive decision
ALT-003 | Open RFI overdue and field work affected | Daily | Superintendent, design manager, PM | rfi_log_clean.csv | Field-impact RFI alert | Critical | One per RFI per day | Protect sequence and assign decision
ALT-004 | Pending change age >35 days | Twice Weekly | Change manager, owner rep, PM | change_orders_clean.csv | Old pending change alert | High | One per item per review cycle | Decide, negotiate, or document disposition
ALT-005 | Pending exposure >1.5% of project budget | Weekly | Executive sponsor, PM, controls | project_workflow_risk_summary.csv | Commercial exposure alert | Critical | Alert only on threshold crossing or weekly unresolved | Approve exposure plan
ALT-006 | Approved change not incorporated or lag >5 days | Weekly | Controls lead, cost manager, PM | change_orders_clean.csv | Forecast control alert | High | Suppress when reconciliation evidence exists | Update forecast
ALT-007 | Revision-loop count exceeds project threshold | Weekly | Design manager, change manager | project_workflow_risk_summary.csv | Workflow quality alert | Medium | Alert on increase or monthly unresolved | Perform root-cause review
ALT-008 | Data quality or row reconciliation fails | Each Refresh | Data analyst, controls lead | process validation outputs | Refresh failure alert | Critical | One alert per failed run | Stop publication and correct data

## RACI
RACI Matrix
R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | Executive Sponsor | Project Manager | Project Controls Lead | Design Manager | Change Manager | Owner Representative | Data Analyst | Superintendent
Top-10 project recovery | A | R | R | C | C | I | I | C
High/Critical RFI resolution | I | A | C | R | I | C | I | C
RFI response standards | I | C | C | A/R | I | C | I | C
Change aging board | I | C | C | I | A/R | R | I | I
Forecast incorporation | I | A | R | I | C | I | I | I
Weekly portfolio dashboard | I | C | A/R | C | C | I | R | I
Automated exception alerts | I | I | A | C | C | I | R | I
Benefits realization | A | C | R | C | C | I | R | I
Threshold and methodology review | A | C | R | C | C | I | R | I
Model governance | A | I | C | I | I | I | R | I

## Benefits_Tracking
Benefits Realization Tracker
Measure realized performance against the validated baseline; do not claim benefits before evidence exists.
Benefit ID | Measure | Baseline | 30-Day Actual | 60-Day Actual | 90-Day Actual | 90-Day Target | Variance to Target | Status | Owner | Evidence
BEN-001 | RFI on-time rate | 45.68% |  |  |  | 70% |  | Not Started | Design Manager | Weekly RFI KPI
BEN-002 | Average RFI response days | 12.21 |  |  |  | 10 |  | Not Started | Design Manager | Weekly RFI KPI
BEN-003 | Average change approval days | 28.91 |  |  |  | 24 |  | Not Started | Change Manager | Change cycle trend
BEN-004 | Pending change exposure | 88104000 |  |  |  | 66078000 |  | Not Started | Change Manager | Change aging report
BEN-005 | Overdue open RFIs | 295 |  |  |  | 148 |  | Not Started | Design Manager | RFI exception report
BEN-006 | Forecast incorporation lag days | 6.58 |  |  |  | 5 |  | Not Started | Project Controls Lead | Forecast reconciliation
BEN-007 | Red projects | 29 |  |  |  | 18 |  | Not Started | Executive Sponsor | Project health dashboard
BEN-008 | Top-10 action closure rate | 0% |  |  |  | 75% |  | Not Started | Project Manager | Action register

## Sources
Sources and Methodology
Project sources and professional lifecycle terminology used in the Act phase.
Source Type | Source | Location / URL | Use
Project data | Executive KPI table | analysis/tables/executive_kpis.csv | Baseline KPI values
Project data | Project workflow risk summary | analysis/tables/project_workflow_risk_summary.csv | Project prioritization
Project data | Top 10 priority projects | analysis/tables/top_10_priority_projects.csv | Project recovery actions
Project data | Workflow bottleneck summary | analysis/tables/workflow_bottleneck_summary.csv | Workflow controls
Project data | Change category summary | analysis/tables/change_category_summary.csv | Commercial priorities
Project data | RFI discipline summary | analysis/tables/rfi_discipline_summary.csv | Discipline priorities
Methodology | IBM CRISP-DM overview | https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=dm-crisp-help-overview | Deployment terminology
Methodology | ASQ DMAIC | https://asq.org/quality-resources/dmaic | Improve and Control terminology
Methodology | Microsoft Data Science Lifecycle | https://learn.microsoft.com/en-us/shows/dev-intro-to-data-science/what-is-the-data-science-lifecycle-2-of-28 | Deployment and customer acceptance
Methodology | PMI Process Groups | https://www.pmi.org/standards/process-groups | Governance and transition terminology
Synthetic-data disclosure: All project names, organizations, people, budgets, schedules, changes, RFIs, and performance records are fictional. The targets and controls are proposed case-study management actions and are not universal industry standards.