## Executive_Summary
Construction Change Order and RFI Analytics
Analyze Phase ¦ Root-cause, cycle-time, impact, bottleneck, and project-priority analysis. All projects, organizations, people, and performance records are synthetic.
90 |  |  | 3318 |  |  | 12.21 | 45.68%
Projects |  |  | RFIs |  |  | Avg RFI Response | RFI On-Time
204568300 |  |  | 88104000 |  |  | 28.91 | 17.15%
Approved Change Value |  |  | Pending Exposure |  |  | Avg Approval Cycle | RFI-to-Change
Workflow Health | Projects
Red | 29
Yellow | 48
Green | 13
Key Analytical Findings
1 | Cross-process speed | Project average RFI response and average change approval have the strongest tested relationship: Pearson r = 0.817 and R² = 0.668.
2 | Decision profile | Slow owner-decision projects averaged 16.45 RFI-response days, 26.3% on-time RFI performance, and 37.98 change-approval days.
3 | Digital coordination | High digital-coordination projects averaged 9.55 response days and 62.0% on-time performance, compared with 14.39 days and 33.6% for Low.
4 | RFI impact driver | Coordination Conflict RFIs generated the greatest actual cost impact: $8.23M, with 533 schedule-impact days.
5 | Change concentration | Owner-directed, design error/omission, and unforeseen-condition changes generated $124.28M in approved value.
Project ID | Project | Risk Score | Health | Avg RFI Days | Avg Approval Days | Pending / Budget
PRJ-006 | Summit Corporate Center | 10 | Red | 11.4848 | 32.5 | 2.658%
PRJ-025 | Canyon Transit-Oriented Development | 9 | Red | 17.0323 | 51 | 2.95%
PRJ-075 | Summit Urban Village | 9 | Red | 18.5833 | 43.625 | 1.403%
PRJ-051 | Evergreen Apartments | 9 | Red | 21.0962 | 45.8571 | 0.562%
PRJ-013 | Aspen Civic Complex 2 | 9 | Red | 10.3947 | 29.5714 | 0.515%
PRJ-016 | Evergreen Town Center | 8 | Red | 17.025 | 35.6 | 1.834%
PRJ-039 | Silver Creek Urban Village 2 | 8 | Red | 12.3077 | 39.3333 | 1.401%
PRJ-019 | Pioneer Research Center | 8 | Red | 14.9423 | 35.8 | 1.26%
PRJ-017 | Mountain Gate Transit Center | 8 | Red | 19.0392 | 33.2 | 0.831%
PRJ-021 | Desert View Processing Plant | 8 | Red | 18 | 36.4545 | 0.172%

## Project_Risk
Project Workflow Risk
Transparent cumulative trigger model. Indicator points are calculated with formulas and linked to the Thresholds sheet.
Project ID | Project Name | Project Type | Delivery Method | Budget | RFI Count | Avg Response Days | On-Time Rate | Overdue Open Rate | High/Critical Overdue Rate | Avg Approval Days | Pending Exposure | Pending / Budget | Forecast Lag Days | Not Incorporated Rate | Response Pts | Overdue Pts | High/Critical Pts | Approval Pts | Pending Pts | Forecast Pts | Not Incorporated Pts | Risk Score | Health
PRJ-006 | Summit Corporate Center | Commercial | Design-Build | 106705000 | 40 | 11.4848 | 45.45% | 17.5% | 7.5% | 32.5 | 2836000 | 2.658% | 10.1429 | 12.5% | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 10 | Red
PRJ-025 | Canyon Transit-Oriented Development | Mixed-Use | IPD | 46069000 | 40 | 17.0323 | 19.35% | 22.5% | 2.5% | 51 | 1359000 | 2.95% | 6.2222 | 0% | 2 | 1 | 1 | 2 | 2 | 1 | 0 | 9 | Red
PRJ-075 | Summit Urban Village | Mixed-Use | CMAR | 242388000 | 55 | 18.5833 | 16.67% | 10.91% | 5.45% | 43.625 | 3400000 | 1.403% | 7.2143 | 12.5% | 2 | 0 | 2 | 2 | 1 | 1 | 1 | 9 | Red
PRJ-051 | Evergreen Apartments | Residential | CMAR | 135815000 | 62 | 21.0962 | 7.69% | 16.13% | 6.45% | 45.8571 | 763000 | 0.562% | 9.1429 | 0% | 2 | 1 | 2 | 2 | 1 | 1 | 0 | 9 | Red
PRJ-013 | Aspen Civic Complex 2 | Institutional | Design-Build | 216138000 | 45 | 10.3947 | 44.74% | 15.56% | 6.67% | 29.5714 | 1114000 | 0.515% | 7.2 | 28.57% | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 9 | Red
PRJ-016 | Evergreen Town Center | Mixed-Use | Design-Build | 191391000 | 43 | 17.025 | 20% | 6.98% | 2.33% | 35.6 | 3511000 | 1.834% | 4.8889 | 10% | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 8 | Red
PRJ-039 | Silver Creek Urban Village 2 | Mixed-Use | CMAR | 80253000 | 40 | 12.3077 | 43.59% | 2.5% | 2.5% | 39.3333 | 1124000 | 1.401% | 9.8 | 16.67% | 1 | 0 | 1 | 2 | 1 | 1 | 2 | 8 | Red
PRJ-019 | Pioneer Research Center | Institutional | Design-Build | 294523000 | 56 | 14.9423 | 26.92% | 7.14% | 7.14% | 35.8 | 3711000 | 1.26% | 6.6429 | 6.67% | 1 | 0 | 2 | 2 | 1 | 1 | 1 | 8 | Red
PRJ-017 | Mountain Gate Transit Center | Heavy Civil & Infrastructure | Design-Bid-Build | 137983000 | 61 | 19.0392 | 15.69% | 16.39% | 3.28% | 33.2 | 1146000 | 0.831% | 6.4444 | 10% | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | Red
PRJ-021 | Desert View Processing Plant | Industrial | Design-Bid-Build | 105525000 | 34 | 18 | 21.21% | 2.94% | 2.94% | 36.4545 | 181000 | 0.172% | 11 | 9.09% | 2 | 0 | 1 | 2 | 0 | 2 | 1 | 8 | Red
PRJ-081 | Desert View Transit-Oriented Development | Mixed-Use | Design-Bid-Build | 140076000 | 38 | 11.1818 | 48.48% | 13.16% | 2.63% | 30.8 | 3374000 | 2.409% | 9.2222 | 10% | 1 | 0 | 1 | 1 | 2 | 1 | 1 | 7 | Red
PRJ-072 | Evergreen Mixed-Use District | Mixed-Use | Design-Bid-Build | 151175000 | 60 | 21.9273 | 10.91% | 8.33% | 0% | 54.7 | 2512000 | 1.662% | 8.1 | 0% | 2 | 0 | 0 | 2 | 2 | 1 | 0 | 7 | Red
PRJ-012 | Canyon Corporate Center | Commercial | CMAR | 30602000 | 60 | 18.4545 | 18.18% | 8.33% | 3.33% | 40.8 | 122000 | 0.399% | 6.7778 | 10% | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 7 | Red
PRJ-068 | Copper Ridge Neighborhood | Residential | CMAR | 19443000 | 34 | 13.1333 | 46.67% | 11.76% | 5.88% | 27 | 73000 | 0.375% | 5.25 | 33.33% | 1 | 0 | 2 | 1 | 0 | 1 | 2 | 7 | Red
PRJ-042 | Blue Mesa Retail Pavilion | Commercial | Design-Build | 23521000 | 30 | 15.6552 | 20.69% | 3.33% | 3.33% | 45.7143 | 88000 | 0.374% | 8.3333 | 14.29% | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 7 | Red
PRJ-067 | Riverbend Housing Community | Residential | CMAR | 19724000 | 36 | 18.9375 | 25% | 11.11% | 2.78% | 41.375 | 55000 | 0.279% | 7.8571 | 12.5% | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 7 | Red
PRJ-008 | Sunset Processing Plant | Industrial | IPD | 93076000 | 48 | 20.7045 | 9.09% | 8.33% | 2.08% | 48.4375 | 192000 | 0.206% | 9 | 6.25% | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 7 | Red
PRJ-029 | Frontier Urban Village 2 | Mixed-Use | Design-Bid-Build | 90078000 | 63 | 15.5893 | 23.21% | 11.11% | 4.76% | 22.3333 | 2479000 | 2.752% | 4 | 0% | 2 | 0 | 1 | 1 | 2 | 0 | 0 | 6 | Red
PRJ-087 | Vista Marketplace 2 | Commercial | CMAR | 17547000 | 20 | 13.25 | 50% | 0% | 0% | 36.3333 | 307000 | 1.75% | 9.1667 | 0% | 1 | 0 | 0 | 2 | 2 | 1 | 0 | 6 | Red
PRJ-057 | Summit Community College | Institutional | IPD | 25635000 | 36 | 11.4516 | 35.48% | 13.89% | 5.56% | 25.3333 | 350000 | 1.365% | 5.3333 | 0% | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 6 | Red
PRJ-080 | Granite Water Facility | Heavy Civil & Infrastructure | CMAR | 306719000 | 30 | 9.0345 | 68.97% | 3.33% | 3.33% | 28.8889 | 3805000 | 1.241% | 10.75 | 11.11% | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 6 | Red
PRJ-065 | Riverbend Marketplace | Commercial | Design-Bid-Build | 43110000 | 29 | 5.3182 | 90.91% | 24.14% | 10.34% | 18.8 | 409000 | 0.949% | 4.3333 | 40% | 0 | 1 | 2 | 0 | 1 | 0 | 2 | 6 | Red
PRJ-036 | Summit Medical Pavilion | Institutional | CMAR | 72447000 | 46 | 15.881 | 19.05% | 8.7% | 0% | 25.375 | 664000 | 0.917% | 7 | 12.5% | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | Red
PRJ-082 | Sunset Office Campus | Commercial | CMAR | 117378000 | 42 | 11.3143 | 42.86% | 16.67% | 4.76% | 18.75 | 1030000 | 0.878% | 7.4286 | 12.5% | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | Red
PRJ-059 | Vista Transit-Oriented Development | Mixed-Use | IPD | 93219000 | 36 | 8.3125 | 65.62% | 11.11% | 11.11% | 20.6 | 335000 | 0.359% | 7.5 | 20% | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 6 | Red
PRJ-026 | Blue Mesa Processing Plant | Industrial | Design-Build | 166383000 | 17 | 5.4667 | 73.33% | 11.76% | 5.88% | 20.75 | 545000 | 0.328% | 8 | 25% | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 6 | Red
PRJ-043 | Copper Ridge Apartments | Residential | CMAR | 66206000 | 35 | 11.1613 | 35.48% | 11.43% | 5.71% | 25.75 | 156000 | 0.236% | 7.5455 | 8.33% | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 6 | Red
PRJ-002 | Northstar Bridge Rehabilitation | Heavy Civil & Infrastructure | Design-Build | 245471000 | 65 | 13.6607 | 37.5% | 13.85% | 9.23% | 29.1818 | 144000 | 0.059% | 5 | 27.27% | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 6 | Red
PRJ-023 | Vista Retail Pavilion | Commercial | IPD | 36537000 | 40 | 18.0811 | 13.51% | 7.5% | 5% | 39 | 0 | 0% | 8.3333 | 0% | 2 | 0 | 1 | 2 | 0 | 1 | 0 | 6 | Red
PRJ-027 | Red Rock Town Center 2 | Mixed-Use | Design-Bid-Build | 244845000 | 56 | 11.1346 | 51.92% | 7.14% | 1.79% | 32.6667 | 5490000 | 2.242% | 5.3333 | 0% | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 5 | Yellow
PRJ-070 | Liberty Manufacturing Facility | Industrial | Design-Bid-Build | 100372000 | 35 | 14.6667 | 21.21% | 5.71% | 0% | 27.5 | 1698000 | 1.692% | 5.6667 | 0% | 1 | 0 | 0 | 1 | 2 | 1 | 0 | 5 | Yellow
PRJ-032 | Blue Mesa Research Center | Institutional | Design-Build | 43278000 | 21 | 8.8095 | 57.14% | 0% | 0% | 27.125 | 652000 | 1.507% | 8.5714 | 12.5% | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 5 | Yellow
PRJ-047 | Desert View Marketplace | Commercial | CMAR | 75198000 | 24 | 7.2727 | 77.27% | 8.33% | 4.17% | 26 | 924000 | 1.229% | 8.1667 | 14.29% | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 5 | Yellow
PRJ-064 | Riverbend Civic Complex | Institutional | Design-Bid-Build | 89816000 | 32 | 11.0741 | 51.85% | 15.62% | 3.12% | 22 | 1051000 | 1.17% | 4 | 0% | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 5 | Yellow
PRJ-090 | Sunset Neighborhood | Residential | IPD | 64382000 | 41 | 11.6765 | 52.94% | 14.63% | 0% | 26.0769 | 542000 | 0.842% | 8 | 7.69% | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | Yellow
PRJ-055 | Desert View Marketplace 2 | Commercial | Design-Build | 137364000 | 38 | 9.5789 | 65.79% | 0% | 0% | 22.5 | 956000 | 0.696% | 8 | 25% | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 5 | Yellow
PRJ-086 | Mountain Gate Processing Plant | Industrial | Design-Bid-Build | 119609000 | 43 | 9.2683 | 51.22% | 4.65% | 2.33% | 22.5 | 761000 | 0.636% | 5 | 33.33% | 0 | 0 | 1 | 1 | 1 | 0 | 2 | 5 | Yellow
PRJ-040 | Pioneer Roadway Program | Heavy Civil & Infrastructure | CMAR | 39982000 | 51 | 17.4091 | 9.09% | 13.73% | 0% | 31.8 | 223000 | 0.558% | 9.2 | 0% | 2 | 0 | 0 | 1 | 1 | 1 | 0 | 5 | Yellow
PRJ-078 | Northstar Community College | Institutional | Design-Bid-Build | 133597000 | 35 | 6.1724 | 72.41% | 17.14% | 5.71% | 8.75 | 668000 | 0.5% | 5.75 | 0% | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 4 | Yellow
PRJ-056 | Riverbend Medical Pavilion | Institutional | Design-Bid-Build | 127656000 | 32 | 21.4483 | 10.34% | 9.38% | 0% | 46.5556 | 356000 | 0.279% | 7.6667 | 0% | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 5 | Yellow
PRJ-049 | Northstar Apartments | Residential | Design-Build | 35381000 | 35 | 13.6207 | 27.59% | 17.14% | 0% | 34 | 63000 | 0.178% | 6.3333 | 14.29% | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 5 | Yellow
PRJ-054 | Summit Processing Plant | Industrial | CMAR | 103115000 | 41 | 15.2703 | 18.92% | 9.76% | 0% | 39.2 | 147000 | 0.143% | 5.6 | 0% | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 5 | Yellow
PRJ-030 | Sunset Corporate Center | Commercial | Design-Build | 28294000 | 35 | 10.9 | 46.67% | 14.29% | 2.86% | 23.1429 | 9800 | 0.035% | 2.2 | 28.57% | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 5 | Yellow
PRJ-003 | Aspen Civic Complex | Institutional | Design-Build | 45069000 | 28 | 10.1304 | 56.52% | 17.86% | 3.57% | 22.2222 | 0 | 0% | 6.3333 | 0% | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 5 | Yellow
PRJ-083 | Sunset Corporate Center 2 | Commercial | Design-Bid-Build | 17645000 | 28 | 8.4231 | 73.08% | 7.14% | 3.57% | 32.5 | 0 | 0% | 5.2 | 16.67% | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 5 | Yellow
PRJ-009 | Granite Office Campus | Commercial | Design-Build | 15695000 | 18 | 9.2353 | 52.94% | 5.56% | 5.56% | 32.6 | 0 | 0% | 4.5 | 20% | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 5 | Yellow
PRJ-045 | Pioneer Community College 2 | Institutional | Design-Build | 141695000 | 44 | 9.425 | 67.5% | 6.82% | 0% | 26.2 | 4488000 | 3.167% | 7.5 | 0% | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 4 | Yellow
PRJ-076 | Vista Marketplace | Commercial | IPD | 194781000 | 43 | 9.0263 | 60.53% | 11.63% | 2.33% | 25.1667 | 5108000 | 2.622% | 4.3333 | 0% | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 4 | Yellow
PRJ-088 | Canyon Transit Center | Heavy Civil & Infrastructure | CMAR | 228698000 | 35 | 9.1143 | 57.14% | 0% | 0% | 19.9 | 5073000 | 2.218% | 3.875 | 20% | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 4 | Yellow
PRJ-046 | Riverbend Apartments | Residential | Design-Build | 31286000 | 38 | 12.0556 | 41.67% | 5.26% | 0% | 33.8333 | 668000 | 2.135% | 4.5 | 0% | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 4 | Yellow
PRJ-033 | Pioneer Apartments | Residential | CMAR | 114252000 | 33 | 11.2581 | 51.61% | 6.06% | 0% | 28.25 | 1655000 | 1.449% | 8.25 | 0% | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 4 | Yellow
PRJ-048 | Vista Medical Pavilion | Institutional | Design-Bid-Build | 213634000 | 51 | 14.0408 | 38.78% | 3.92% | 0% | 35.5294 | 2246000 | 1.051% | 4.8235 | 0% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 4 | Yellow
PRJ-035 | Canyon Apartments | Residential | Design-Bid-Build | 41279000 | 48 | 12.6222 | 35.56% | 6.25% | 0% | 47.4286 | 363000 | 0.879% | 2.8571 | 0% | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 4 | Yellow
PRJ-053 | Copper Ridge Office Campus | Commercial | Design-Bid-Build | 35443000 | 32 | 8.6 | 66.67% | 6.25% | 0% | 22.2727 | 263000 | 0.742% | 4.4444 | 18.18% | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 4 | Yellow
PRJ-031 | Mountain Gate Water Facility | Heavy Civil & Infrastructure | IPD | 51859000 | 37 | 9.303 | 60.61% | 10.81% | 5.41% | 21 | 337000 | 0.65% | 3.625 | 0% | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 4 | Yellow
PRJ-052 | Copper Ridge Retail Pavilion | Commercial | Design-Build | 37364000 | 23 | 12.3182 | 45.45% | 4.35% | 0% | 25.3333 | 242000 | 0.648% | 7.6667 | 0% | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 4 | Yellow
PRJ-079 | Summit Retail Pavilion 2 | Commercial | Design-Build | 155934000 | 43 | 10.825 | 45% | 6.98% | 4.65% | 18.8 | 577000 | 0.37% | 8.3333 | 10% | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 4 | Yellow
PRJ-011 | Aspen Retail Pavilion | Commercial | Design-Build | 46836000 | 34 | 10.0968 | 45.16% | 8.82% | 2.94% | 27.8 | 111000 | 0.237% | 5.3 | 0% | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 4 | Yellow
PRJ-022 | Frontier Urban Village | Mixed-Use | Design-Bid-Build | 218801000 | 44 | 8.3243 | 78.38% | 15.91% | 2.27% | 14.2857 | 403000 | 0.184% | 6.1667 | 14.29% | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 4 | Yellow
PRJ-077 | Silver Creek Retail Pavilion | Commercial | CMAR | 202367000 | 67 | 15.6667 | 19.05% | 5.97% | 2.99% | 31.5 | 309000 | 0.153% | 4.6667 | 0% | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 4 | Yellow
PRJ-018 | Frontier Manufacturing Facility | Industrial | CMAR | 329366000 | 47 | 7.1026 | 84.62% | 17.02% | 8.51% | 15.625 | 150000 | 0.046% | 6 | 0% | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 4 | Yellow
PRJ-050 | Evergreen Corporate Center | Commercial | CMAR | 176226000 | 26 | 6.125 | 75% | 7.69% | 3.85% | 14.6 | 0 | 0% | 8 | 20% | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 4 | Yellow
PRJ-034 | Summit Retail Pavilion | Commercial | Design-Bid-Build | 39832000 | 30 | 15.5 | 28.57% | 6.67% | 0% | 30.6364 | 0 | 0% | 5.0909 | 0% | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 4 | Yellow
PRJ-089 | Evergreen Housing Community | Residential | Design-Bid-Build | 28248000 | 22 | 8.1429 | 80.95% | 4.55% | 4.55% | 18.3333 | 0 | 0% | 10.125 | 11.11% | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 4 | Yellow
PRJ-004 | Silver Creek Urban Village | Mixed-Use | Design-Bid-Build | 103276000 | 29 | 5.0769 | 92.31% | 10.34% | 3.45% | 15.7143 | 1355000 | 1.312% | 7.5714 | 0% | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 3 | Yellow
PRJ-005 | Red Rock Civic Complex | Institutional | IPD | 85679000 | 28 | 8.6429 | 64.29% | 0% | 0% | 28.3333 | 1093000 | 1.276% | 6.6667 | 0% | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | Yellow
PRJ-058 | Mountain Gate Housing Community | Residential | Design-Build | 39523000 | 30 | 8.8621 | 68.97% | 3.33% | 0% | 19.5 | 408000 | 1.032% | 1 | 50% | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 3 | Yellow
PRJ-071 | Mountain Gate Marketplace | Commercial | Design-Bid-Build | 113195000 | 32 | 10 | 57.14% | 12.5% | 3.12% | 17.8889 | 1105000 | 0.976% | 5.3333 | 0% | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 3 | Yellow
PRJ-063 | Canyon Urban Village | Mixed-Use | Design-Build | 199081000 | 39 | 6.5946 | 81.08% | 5.13% | 0% | 19.8 | 1264000 | 0.635% | 3.75 | 20% | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 3 | Yellow
PRJ-038 | Northstar Neighborhood | Residential | Design-Bid-Build | 95451000 | 24 | 5.8696 | 82.61% | 4.17% | 0% | 24.75 | 326000 | 0.342% | 7.5714 | 12.5% | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 3 | Yellow
PRJ-024 | Pioneer Community College | Institutional | Design-Build | 75829000 | 35 | 14.3143 | 20% | 0% | 0% | 27.8333 | 196000 | 0.258% | 6.5833 | 0% | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | Yellow
PRJ-037 | Vista Civic Complex | Institutional | Design-Bid-Build | 92832000 | 35 | 11.9697 | 48.48% | 5.71% | 2.86% | 34.1429 | 213000 | 0.229% | 4 | 0% | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | Yellow
PRJ-069 | Granite Medical Pavilion | Institutional | CMAR | 25315000 | 27 | 12.84 | 52% | 7.41% | 0% | 28.6667 | 50000 | 0.198% | 7.1667 | 0% | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | Yellow
PRJ-014 | Riverbend Retail Pavilion | Commercial | Design-Bid-Build | 104424000 | 26 | 10.4 | 56% | 3.85% | 0% | 28.5 | 0 | 0% | 6.5 | 0% | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | Yellow
PRJ-010 | Canyon Neighborhood | Residential | Design-Build | 35406000 | 27 | 10.6923 | 61.54% | 3.7% | 0% | 32.5 | 0 | 0% | 5 | 10% | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 3 | Yellow
PRJ-001 | Red Rock Town Center | Mixed-Use | CMAR | 330355000 | 29 | 6.75 | 78.57% | 3.45% | 0% | 12.7857 | 0 | 0% | 5.8 | 28.57% | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | Yellow
PRJ-007 | Canyon Medical Pavilion | Institutional | Design-Build | 43072000 | 38 | 11.6111 | 47.22% | 2.63% | 0% | 26.1111 | 0 | 0% | 9.1111 | 0% | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | Yellow
PRJ-041 | Riverbend Transit-Oriented Development | Mixed-Use | CMAR | 260515000 | 28 | 7.1923 | 69.23% | 7.14% | 0% | 19.3333 | 4507000 | 1.73% | 3.8333 | 0% | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | Green
PRJ-028 | Canyon Bridge Rehabilitation | Heavy Civil & Infrastructure | CMAR | 73292000 | 28 | 12.8846 | 42.31% | 7.14% | 0% | 19 | 959000 | 1.308% | 4.25 | 0% | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | Green
PRJ-066 | Liberty Civic Complex | Institutional | CMAR | 172986000 | 35 | 6.7188 | 59.38% | 8.57% | 2.86% | 17.2 | 399000 | 0.231% | 9.8 | 0% | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | Green
PRJ-062 | Copper Ridge Housing Community | Residential | Design-Bid-Build | 15016000 | 30 | 7.1724 | 79.31% | 3.33% | 0% | 14.7778 | 34200 | 0.228% | 7.125 | 11.11% | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | Green
PRJ-073 | Blue Mesa Apartments | Residential | CMAR | 31695000 | 41 | 13.4474 | 28.95% | 7.32% | 0% | 32.75 | 66000 | 0.208% | 4.5 | 0% | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | Green
PRJ-074 | Canyon Distribution Center | Industrial | Design-Build | 31649000 | 28 | 9 | 74.07% | 3.57% | 3.57% | 25.1667 | 50000 | 0.158% | 4.5 | 0% | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | Green
PRJ-085 | Red Rock Community College | Institutional | CMAR | 72110000 | 24 | 8 | 63.64% | 8.33% | 0% | 13.8 | 976000 | 1.353% | 5 | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Green
PRJ-044 | Sunset Processing Plant 2 | Industrial | CMAR | 194536000 | 31 | 6.2759 | 100% | 6.45% | 0% | 14 | 1262000 | 0.649% | 5 | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Green
PRJ-020 | Aspen Processing Plant | Industrial | Design-Bid-Build | 216015000 | 30 | 8.4138 | 68.97% | 3.33% | 0% | 16.8571 | 1247000 | 0.577% | 3.8571 | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Green
PRJ-060 | Summit Medical Pavilion 2 | Institutional | Design-Build | 26794000 | 22 | 9.7143 | 47.62% | 4.55% | 0% | 18 | 88000 | 0.328% | 8 | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | Green
PRJ-061 | Red Rock Distribution Center | Industrial | Design-Bid-Build | 231610000 | 37 | 6.9167 | 69.44% | 2.7% | 0% | 15.8571 | 894000 | 0.386% | 4.7143 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Green
PRJ-084 | Northstar Retail Pavilion | Commercial | Design-Bid-Build | 179971000 | 28 | 5.6 | 84% | 10.71% | 0% | 14.1667 | 281000 | 0.156% | 4.5 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Green
PRJ-015 | Evergreen Retail Pavilion | Commercial | CMAR | 16767000 | 26 | 8.76 | 72% | 3.85% | 0% | 16.6667 | 12000 | 0.072% | 3.8333 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Green

## RFI_Discipline
RFI Performance by Discipline
Response speed, compliance, linkage, and impact.
Discipline | RFI_Count | Responded_Count | Avg_Response_Days | On_Time_Rate_Pct | Overdue_Open_Count | RFI_to_Change_Rate_Pct | Cost_Impacted_Count | Schedule_Impacted_Count | Actual_Cost_Impact | Actual_Schedule_Days
Specialty Systems | 231 | 211 | 13.64 | 41.2% | 20 | 14.7% | 46 | 35 | 1872400 | 188
Mechanical | 480 | 439 | 13.43 | 38.7% | 40 | 19.2% | 117 | 90 | 4939500 | 365
Electrical | 518 | 468 | 12.98 | 42.5% | 50 | 17.8% | 122 | 82 | 5146900 | 436
Structural | 413 | 370 | 12.95 | 41.1% | 43 | 17.4% | 95 | 83 | 2972300 | 302
Fire Protection | 181 | 173 | 12.41 | 43.4% | 8 | 16.6% | 44 | 32 | 2022800 | 152
Civil | 285 | 263 | 12.38 | 44.9% | 21 | 17.5% | 70 | 48 | 2363600 | 219
Controls | 157 | 147 | 12.18 | 49% | 10 | 19.1% | 38 | 22 | 1821600 | 158
Plumbing | 283 | 255 | 11.18 | 48.6% | 28 | 13.4% | 59 | 44 | 2997100 | 229
Architectural | 495 | 441 | 10.89 | 51% | 53 | 16.8% | 99 | 86 | 3309000 | 316
General | 275 | 252 | 9.46 | 62.3% | 22 | 17.5% | 56 | 40 | 2163300 | 207

## RFI_Type
RFI Performance by Type
Root-cause category, response, linkage, and cost/schedule impact.
RFI_Type | RFI_Count | Avg_Response_Days | On_Time_Rate_Pct | Overdue_Open_Count | RFI_to_Change_Rate_Pct | Cost_Impacted_Count | Schedule_Impacted_Count | Actual_Cost_Impact | Actual_Schedule_Days
Coordination Conflict | 757 | 12.32 | 46.9% | 78 | 18.9% | 191 | 136 | 8225100 | 533
Design Clarification | 872 | 12.21 | 47.3% | 79 | 13.3% | 156 | 117 | 6777000 | 449
Missing Information | 478 | 12.25 | 42.9% | 46 | 18% | 111 | 85 | 4057500 | 525
Constructability | 404 | 11.76 | 45.9% | 36 | 16.3% | 86 | 63 | 3651100 | 269
Field Condition | 386 | 12.12 | 44% | 25 | 21% | 111 | 91 | 3559900 | 494
Substitution Request | 259 | 12.65 | 42.2% | 20 | 19.7% | 58 | 45 | 2436100 | 211
Code Compliance | 162 | 12.31 | 48.3% | 11 | 16% | 33 | 25 | 901800 | 91

## Change_Category
Change Order Analysis by Category
Approved value, pending exposure, schedule impact, and cycle time.
Change_Category | Change_Count | Approved_Count | Pending_Count | Approved_Value | Pending_Exposure | Avg_Approval_Days | Approved_Schedule_Days | Linked_Change_Count | Avg_Forecast_Lag_Days
Owner-Directed Change | 198 | 126 | 41 | 44093100 | 22849000 | 32.33 | 454 | 46 | 7.28
Design Error or Omission | 197 | 118 | 41 | 40302400 | 14907000 | 32.92 | 216 | 135 | 6.32
Unforeseen Condition | 168 | 108 | 29 | 39882000 | 17020000 | 28.41 | 275 | 114 | 6.9
Code or Regulatory Requirement | 78 | 54 | 10 | 16442100 | 6094000 | 31.96 | 66 | 37 | 6.32
Substitution | 94 | 60 | 22 | 14284000 | 6963000 | 25.77 | 81 | 51 | 6.47
Value Engineering | 93 | 62 | 19 | 13922100 | 5604000 | 24.6 | 149 | 37 | 5.55
Schedule Acceleration | 78 | 49 | 15 | 13904000 | 2254000 | 30.04 | 119 | 41 | 5.72
Quantity Variation | 106 | 65 | 19 | 11806400 | 6831000 | 23.74 | 119 | 55 | 7.9
Scope Clarification | 107 | 64 | 25 | 9932200 | 5582000 | 24.53 | 59 | 61 | 5.9

## Workflow_Bottlenecks
Workflow Bottleneck Analysis
Stage duration, volume, handoffs, and revision-loop concentration.
Item_Type | To_Status | Assigned_To_Role | Event_Count | Avg_Stage_Days | Total_Stage_Days | Handoff_Count | Revision_Loop_Count
Change Order | Approved | Project Manager | 706 | 20.31 | 14335.35 | 706 | 0
RFI | Closed | Subcontractor | 948 | 9.93 | 9411.6 | 756 | 0
RFI | Closed | General Contractor | 925 | 9.57 | 8854.16 | 696 | 0
Change Order | Returned for Revision | Cost Manager | 512 | 16.7 | 8552.62 | 511 | 512
Change Order | Submitted | Owner Representative | 1117 | 7.03 | 7850.68 | 1117 | 0
RFI | Returned for Clarification | General Contractor | 344 | 11.95 | 4109.42 | 344 | 344
RFI | Returned for Clarification | Subcontractor | 308 | 10.86 | 3345.12 | 308 | 308
RFI | Answered | General Contractor | 350 | 9.48 | 3319.07 | 267 | 0
Change Order | Rejected | Project Manager | 113 | 28.89 | 3264.7 | 113 | 0
RFI | Answered | Subcontractor | 337 | 9.64 | 3247.93 | 257 | 0
RFI | Closed | Construction Manager | 332 | 9.75 | 3235.64 | 229 | 0
Change Order | Pending | Project Manager | 220 | 14.03 | 3086.36 | 220 | 0
Change Order | Withdrawn | Project Manager | 79 | 22.33 | 1763.96 | 79 | 0
RFI | Returned for Clarification | Construction Manager | 134 | 11.01 | 1475.78 | 119 | 134
RFI | Answered | Construction Manager | 127 | 9.64 | 1224.9 | 81 | 0
RFI | In Review | Engineer | 54 | 7.41 | 400.18 | 4 | 0
RFI | Awaiting Designer | Engineer | 39 | 7.69 | 299.81 | 6 | 0
RFI | Open | Engineer | 30 | 7.41 | 222.43 | 7 | 0
RFI | Returned for Clarification | Engineer | 24 | 8.06 | 193.49 | 3 | 24
RFI | Awaiting Owner | Engineer | 28 | 5.93 | 166.17 | 7 | 0
RFI | Awaiting Owner | Architect | 13 | 8.79 | 114.27 | 2 | 0
RFI | In Review | Architect | 16 | 7.1 | 113.66 | 2 | 0
RFI | Awaiting Designer | Owner Representative | 11 | 6.64 | 73.01 | 2 | 0

## Segment_Analysis
Operating Segment Analysis
Decision profile and digital-coordination comparisons.
Segment_Type | Segment | RFI_Count | Avg_RFI_Response_Days | On_Time_Rate_Pct | Change_Count | Avg_Approval_Cycle_Days | Pending_Exposure
Owner Decision Profile | Fast | 597 | 10.4 | 52.8% | 197 | 24.36 | 12516000
Owner Decision Profile | Standard | 1905 | 11.01 | 51.5% | 623 | 26.01 | 52494000
Owner Decision Profile | Slow | 816 | 16.45 | 26.3% | 299 | 37.98 | 23094000
Digital Coordination Level | High | 881 | 9.55 | 62% | 304 | 26.39 | 25448200
Digital Coordination Level | Moderate | 1675 | 12.63 | 42.5% | 567 | 30.02 | 48307800
Digital Coordination Level | Low | 762 | 14.39 | 33.6% | 248 | 29.29 | 14348000
Year | RFI_Count | Avg_RFI_Response_Days | On_Time_Rate_Pct | Change_Count | Approved_Value | Avg_Approval_Cycle_Days | Pending_Exposure
2022 | 849 | 12.17 | 47.5% | 280 | 60931300 | 27.77 | 25670800
2023 | 1011 | 12.67 | 41.9% | 355 | 66323500 | 28.76 | 22475200
2024 | 958 | 12.13 | 45.6% | 320 | 44240500 | 31.38 | 23242000
2025 | 500 | 11.52 | 50.6% | 164 | 33073000 | 26.49 | 16716000

## Associations
Statistical Associations
Synthetic-data relationships; correlation does not establish causation.
Relationship | Method | Statistic | P_Value | N | Interpretation
RFI response days vs cost-impact flag | Point-biserial r | 0.2891 | 3.2756e-59 | 3019 | Longer response time shows a moderate positive association with cost impact.
RFI response days vs schedule-impact flag | Point-biserial r | 0.2336 | 1.0622e-38 | 3019 | Longer response time shows a modest positive association with schedule impact.
RFI response days vs linked-to-change flag | Point-biserial r | 0.0431 | 0.017755 | 3019 | Response time alone has only a weak association with later change linkage.
RFI revision count vs response days | Spearman rho | 0.4315 | 3.4412e-137 | 3019 | More revision activity is moderately associated with longer response cycles.
RFI reopen count vs response days | Spearman rho | 0.265 | 1.0602e-49 | 3019 | Reopened RFIs are associated with longer response cycles.
RFI response quality vs response days | Spearman rho | -0.5102 | 8.7067e-200 | 3019 | Longer response cycles are associated with lower response-quality ratings in the synthetic data.
Change revision count vs approval days | Spearman rho | 0.4683 | 9.058e-40 | 706 | More change revisions are moderately associated with longer approval cycles.
Change submitted value vs approval days | Spearman rho | 0.0222 | 0.55659 | 706 | Change size has little association with approval cycle in this portfolio.
Change linked-to-RFI flag vs approval days | Point-biserial r | 0.001 | 0.97809 | 706 | Linked and unlinked changes have essentially the same approval-cycle distribution.
Project average RFI response vs average change approval cycle | Pearson r | 0.8172 | 8.9473e-23 | 90 | Projects with slower RFI response also tend to have slower change approval; this is the strongest tested portfolio-level relationship.
Project average RFI response vs average change approval cycle | Spearman rho | 0.8038 | 1.4812e-21 | 90 | The strong monotonic relationship is consistent with the Pearson result.

## Model_Results
Exploratory RFI-to-Change Models
Diagnostic evidence only. No model is approved for production use.
Model | Available_Information | Mean_CV_AUC | Std_CV_AUC | Fold_AUCs | Interpretation | Production_Use
Submission-only exploratory logistic model | Priority, RFI type, discipline, roles, drawing count, project attributes | 0.5096 | 0.0206 | 0.4965; 0.4893; 0.5319; 0.5372; 0.4932 | Performance is near chance; submission attributes alone do not identify later change linkage in this synthetic portfolio. | No
Diagnostic exploratory logistic model | Submission attributes plus response, revision, quality, and impact indicators | 0.6311 | 0.0307 | 0.6375; 0.6451; 0.6686; 0.5758; 0.6284 | Post-submission workflow and impact indicators improve discrimination, but performance remains moderate. | No
Governance conclusion: submission-only attributes were approximately chance-level (AUC 0.510). Post-submission workflow and impact indicators improved AUC to 0.631, but some occur after the initial decision point. A real deployment would require temporal validation, leakage controls, calibration, subgroup testing, monitoring, and stakeholder acceptance.

## Thresholds
Workflow Risk Thresholds
Case-study assumptions used for transparent project prioritization.
Indicator | Yellow Threshold | Red Threshold | Workbook Input | Interpretation
Average RFI response | 10 | 15 | days | Higher is worse
Overdue open rate | 15% | 30% | percent | Higher is worse
High/Critical overdue rate | 2% | 5% | percent | Higher is worse
Average change approval | 20 | 35 | days | Higher is worse
Pending exposure / budget | 0.5% | 1.5% | percent | Higher is worse
Average forecast lag | 5 | 10 | days | Higher is worse
Approved not incorporated rate | 5% | 15% | percent | Higher is worse
Overall Status | Yellow Minimum | Red Minimum
Risk Score | 3 | 6
Scoring: each indicator receives 0 points when Green, 1 point when Yellow, and 2 points when Red. Overall status is Green for 0–2 points, Yellow for 3–5 points, and Red for 6 or more points. The thresholds are portfolio assumptions, not universal standards.

## Sources
Sources and Reproducibility
Source Type | Source | Location / URL | Use
Project data | Validated clean SQLite database | data/processed/construction_change_order_rfi_analytics.sqlite | Primary analytical source
Project data | Clean RFI log | data/cleaned/rfi_log_clean.csv | RFI response and impact analysis
Project data | Clean change orders | data/cleaned/change_orders_clean.csv | Approval, exposure, and impact analysis
Project data | Workflow events | data/cleaned/workflow_events_clean.csv | Stage duration, handoff, and revision-loop analysis
Project data | RFI/change bridge | data/cleaned/rfi_change_links_clean.csv | Conversion and relationship analysis
Methodology | IBM CRISP-DM overview | https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=dm-crisp-help-overview | Lifecycle terminology
Methodology | ASQ DMAIC | https://asq.org/quality-resources/dmaic | Process-improvement terminology
Methodology | Microsoft Data Science Lifecycle | https://learn.microsoft.com/en-us/shows/dev-intro-to-data-science/what-is-the-data-science-lifecycle-2-of-28 | Modeling and deployment terminology
Methodology | PMI Process Groups | https://www.pmi.org/standards/process-groups | Project-governance terminology
Synthetic-data disclosure: All project names, organizations, people, budgets, schedules, changes, RFIs, and performance records are fictional and were created for education, portfolio demonstration, and analytical-methodology development. They do not represent actual In Project LLC clients or confidential construction records.