## Overview
Construction Change Order and RFI Analytics - Data Dictionary
Synthetic relational dataset for workflow, cycle-time, impact, bottleneck, and RFI-to-change analysis. All records are fictional.
Table | Grain | Primary Key | Raw Rows | Intended Unique Rows | Purpose
Projects | One row per project | Project_ID | 92 | 90 | Portfolio and project attributes
RFI Log | One row per RFI | RFI_ID | 3328 | 3320 | Response, aging, impact, and status analysis
Change Orders | One row per change item | Change_Order_ID | 1125 | 1120 | Cost, approval, aging, and schedule-impact analysis
Workflow Events | One row per transition/handoff | Event_ID | 11308 | 11298 | Stage duration, queue, loop, and bottleneck analysis
RFI Change Links | One row per explicit relationship | Link_ID | 683 | 680 | Many-to-many RFI/change analysis
Relationship | Parent | Child | Cardinality | Foreign Key | Validation
Project RFIs | Projects | RFI Log | 1:M | Project_ID | Every RFI parent must exist
Project Changes | Projects | Change Orders | 1:M | Project_ID | Every change parent must exist
Project Events | Projects | Workflow Events | 1:M | Project_ID | Every event parent must exist
RFI/Change Bridge | RFI Log | RFI Change Links | 1:M | RFI_ID | Every linked RFI must exist
RFI/Change Bridge | Change Orders | RFI Change Links | 1:M | Change_Order_ID | Every linked change must exist
Workflow Item | RFI or Change Order | Workflow Events | 1:M | Item_ID + Item_Type | Polymorphic validation required
Raw-data note: the raw files intentionally contain documented duplicates, category variants, missing values, invalid date sequences, numerical anomalies, and invalid foreign keys. Cleaning occurs only in the Process phase.

## Projects
Projects - Field Dictionary
Field | Data Type | Nullable | Key / Relationship | Valid Values / Rule | Definition | Example | Primary Analytical Use
Project_ID | Text | No | Primary key | Pattern PRJ-### | Unique fictional project identifier | PRJ-001 | Join, filtering, and record traceability
Project_Name | Text | No |  | Synthetic project name | Portfolio identification | Red Rock Town Center | Descriptive segmentation and business context
Project_Type | Text | No |  | Controlled project type | Segmentation | Mixed-Use | Segmentation and root-cause comparison
City | Text | No |  | Synthetic U.S. city | Location analysis | Scottsdale | Descriptive segmentation and business context
State | Text | No |  | Two-letter state code | Location analysis | AZ | Descriptive segmentation and business context
Region | Text | No |  | Controlled region | Regional segmentation | Southwest | Descriptive segmentation and business context
Client_Type | Text | No |  | Controlled client type | Client comparison | Private Developer | Segmentation and root-cause comparison
Contract_Type | Text | No |  | Controlled contract structure | Commercial comparison | Cost Plus | Segmentation and root-cause comparison
Delivery_Method | Text | No |  | Controlled delivery method | Delivery comparison | CMAR | Descriptive segmentation and business context
Complexity_Level | Text | No |  | Low/Moderate/High/Very High | Complexity segmentation | Low | Descriptive segmentation and business context
Digital_Coordination_Level | Text | No |  | Low/Moderate/High | Coordination maturity | Moderate | Descriptive segmentation and business context
Owner_Decision_Profile | Text | No |  | Fast/Standard/Slow | Decision-cycle segmentation | Standard | Descriptive segmentation and business context
Original_Budget | Currency | No |  | Nonnegative | Project scale and normalization | 330355000 | Cost exposure and normalization
Original_Contingency | Currency | No |  | Nonnegative | Risk and exposure context | 16476000 | Cost exposure and normalization
Planned_Start_Date | Date | No |  | ISO date | Schedule context | 2024-04-10 | Cycle-time, aging, and sequence analysis
Planned_End_Date | Date | No |  | Must follow planned start | Schedule context | 2025-04-10 | Cycle-time, aging, and sequence analysis
Actual_Start_Date | Date | No |  | ISO date | Actual schedule context | 2024-04-01 | Cycle-time, aging, and sequence analysis
Forecast_End_Date | Date | No |  | May extend beyond cutoff | Forecast schedule context | 2025-04-23 | Cycle-time, aging, and sequence analysis
Project_Status | Text | No |  | Controlled status | Portfolio status | Completed | Funnel, backlog, and workflow-state analysis
Current_Phase | Text | No |  | Controlled phase | Phase comparison | Closeout | Descriptive segmentation and business context
Project_Manager_ID | Text | No |  | Pattern PM-### | Synthetic accountability role | PM-015 | Join, filtering, and record traceability
Design_Manager_ID | Text | No |  | Pattern DM-### | Synthetic accountability role | DM-008 | Join, filtering, and record traceability
Change_Manager_ID | Text | No |  | Pattern CM-### | Synthetic accountability role | CM-001 | Join, filtering, and record traceability

## RFI_Log
RFI Log - Field Dictionary
Field | Data Type | Nullable | Key / Relationship | Valid Values / Rule | Definition | Example | Primary Analytical Use
RFI_ID | Text | No | Primary key | Pattern RFI-##### | Unique RFI identifier | RFI-00001 | Join, filtering, and record traceability
Project_ID | Text | No | FK Projects | Must exist in Projects | Project relationship | PRJ-001 | Join, filtering, and record traceability
RFI_Number | Text | No |  | Project-local RFI number | Project reporting | RFI-0001 | Descriptive segmentation and business context
RFI_Title | Text | No |  | Synthetic issue description | Human-readable context | Architectural Substitution Request - Area A2 | Descriptive segmentation and business context
Discipline | Text | No |  | Controlled discipline | Discipline comparison | Architectural | Segmentation and root-cause comparison
Priority | Text | No |  | Low/Medium/High/Critical | Service-level analysis | Medium | Segmentation and root-cause comparison
RFI_Type | Text | No |  | Controlled issue type | Root-cause analysis | Substitution Request | Segmentation and root-cause comparison
Submitted_Date | Date | No |  | ISO date | Cycle-time start | 2024-08-18 | Cycle-time, aging, and sequence analysis
Required_Response_Date | Date | No |  | On/after submission | SLA compliance | 2024-08-27 | Cycle-time, aging, and sequence analysis
First_Response_Date | Date | Yes |  | On/after submission | First-touch performance | 2024-08-25 | Cycle-time, aging, and sequence analysis
Final_Response_Date | Date | Yes |  | On/after submission | Final response cycle | 2024-08-28 | Cycle-time, aging, and sequence analysis
Closed_Date | Date | Yes |  | On/after final response | Closure cycle | 2024-08-31 | Cycle-time, aging, and sequence analysis
RFI_Status | Text | No |  | Controlled status | Backlog and funnel | Closed | Funnel, backlog, and workflow-state analysis
Submitted_By_Role | Text | No |  | Controlled role | Originator analysis | Subcontractor | Responsibility, ownership, and handoff analysis
Responsible_Role | Text | No |  | Controlled role | Accountability analysis | Architect | Responsibility, ownership, and handoff analysis
Revision_Count | Whole number | No |  | Nonnegative | Revision-loop analysis | 1 | Frequency, quality, and process-loop analysis
Reopen_Count | Whole number | No |  | Nonnegative | First-pass resolution | 0 | Frequency, quality, and process-loop analysis
Cost_Impact_Flag | Text | No |  | Yes/No | Impact rate | No | Cost exposure and normalization
Estimated_Cost_Impact | Currency | No |  | Nonnegative under standard convention | Impact estimation | 0 | Cost exposure and normalization
Actual_Cost_Impact | Currency | No |  | Nonnegative under standard convention | Observed impact | 0 | Cost exposure and normalization
Schedule_Impact_Flag | Text | No |  | Yes/No | Impact rate | No | Schedule-impact and cycle-time analysis
Estimated_Schedule_Days | Whole number | No |  | Nonnegative | Schedule exposure | 0 | Schedule-impact and cycle-time analysis
Actual_Schedule_Days | Whole number | No |  | Nonnegative | Observed schedule impact | 0 | Schedule-impact and cycle-time analysis
Field_Work_Affected | Text | No |  | Yes/No | Field-decision analysis | No | Impact-rate and exception analysis
Drawing_Reference_Count | Whole number | No |  | Nonnegative | Document complexity | 1 | Frequency, quality, and process-loop analysis
Response_Quality_Rating | Whole number | No |  | 1 to 5 | Response quality | 4 | Frequency, quality, and process-loop analysis

## Change_Orders
Change Orders - Field Dictionary
Field | Data Type | Nullable | Key / Relationship | Valid Values / Rule | Definition | Example | Primary Analytical Use
Change_Order_ID | Text | No | Primary key | Pattern CO-##### | Unique change identifier | CO-00001 | Join, filtering, and record traceability
Project_ID | Text | No | FK Projects | Must exist in Projects | Project relationship | PRJ-001 | Join, filtering, and record traceability
Change_Number | Text | No |  | Project-local number | Project reporting | CO-001 | Descriptive segmentation and business context
Change_Title | Text | No |  | Synthetic change description | Human-readable context | Substitution - Mechanical Area B6 | Descriptive segmentation and business context
Change_Category | Text | No |  | Controlled category | Root-cause analysis | Substitution | Segmentation and root-cause comparison
Initiating_Party | Text | No |  | Controlled party | Source analysis | Construction Manager | Responsibility, ownership, and handoff analysis
Discipline | Text | No |  | Controlled discipline | Discipline comparison | Mechanical | Segmentation and root-cause comparison
Change_Type | Text | No |  | Additive/Deductive/Zero-Cost/Time Only | Commercial classification | Additive | Segmentation and root-cause comparison
Originating_Source | Text | No |  | Controlled source | Workflow origin | Field Condition | Descriptive segmentation and business context
Identified_Date | Date | No |  | ISO date | Lifecycle start | 2024-12-28 | Cycle-time, aging, and sequence analysis
Submitted_Date | Date | No |  | On/after identified date | Approval-cycle start | 2024-12-31 | Cycle-time, aging, and sequence analysis
Required_Decision_Date | Date | No |  | On/after submission | Decision SLA | 2025-01-20 | Cycle-time, aging, and sequence analysis
First_Decision_Date | Date | Yes |  | On/after submission | First-touch analysis | 2025-01-05 | Cycle-time, aging, and sequence analysis
Approved_Date | Date | Yes |  | Required for approved items | Approval cycle | 2025-01-08 | Cycle-time, aging, and sequence analysis
Closed_Date | Date | Yes |  | Required for final disposition | Closure cycle | 2025-01-18 | Cycle-time, aging, and sequence analysis
Change_Status | Text | No |  | Controlled status | Backlog and funnel | Approved | Funnel, backlog, and workflow-state analysis
Submitted_Value | Currency | No |  | Signed value permitted for deductive changes | Exposure | 1173000 | Cost exposure and normalization
Negotiated_Value | Currency | Yes |  | Signed value | Negotiation variance | 978000 | Cost exposure and normalization
Approved_Value | Currency | Yes |  | Required for approved items | Authorized cost impact | 978000 | Cost exposure and normalization
Requested_Schedule_Days | Whole number | No |  | Nonnegative under extension convention | Requested time impact | 0 | Schedule-impact and cycle-time analysis
Approved_Schedule_Days | Whole number | No |  | Nonnegative | Authorized time impact | 0 | Schedule-impact and cycle-time analysis
Revision_Count | Whole number | No |  | Nonnegative | Revision-loop analysis | 0 | Frequency, quality, and process-loop analysis
Pricing_Status | Text | No |  | Controlled status | Commercial readiness | Final | Funnel, backlog, and workflow-state analysis
Authorization_Type | Text | No |  | Controlled authorization | Governance analysis | Owner Authorization | Segmentation and root-cause comparison
Forecast_Incorporated_Date | Date | Yes |  | On/after approval | Forecast-control lag | 2025-01-16 | Cycle-time, aging, and sequence analysis
Cost_Code_Group | Text | No |  | Controlled cost group | Cost segmentation | Sitework | Cost exposure and normalization

## Workflow_Events
Workflow Events - Field Dictionary
Field | Data Type | Nullable | Key / Relationship | Valid Values / Rule | Definition | Example | Primary Analytical Use
Event_ID | Text | No | Primary key | Pattern EVT-###### | Unique event identifier | EVT-000001 | Join, filtering, and record traceability
Project_ID | Text | No | FK Projects | Must exist in Projects | Project relationship | PRJ-001 | Join, filtering, and record traceability
Item_Type | Text | No | Polymorphic parent | RFI or Change Order | Selects item parent table | RFI | Segmentation and root-cause comparison
Item_ID | Text | No | Polymorphic FK | Must exist in selected parent table | Workflow relationship | RFI-00001 | Join, filtering, and record traceability
Event_Sequence | Whole number | No |  | Positive sequence by item | Stage ordering | 1 | Descriptive segmentation and business context
Event_Timestamp | DateTime | No |  | ISO date-time; observed through cutoff | Cycle and queue timing | 2024-08-18T08:00 | Cycle-time, aging, and sequence analysis
From_Status | Text | Yes |  | Controlled status or blank for creation | Transition origin |  | Funnel, backlog, and workflow-state analysis
To_Status | Text | No |  | Controlled status | Transition destination | Submitted | Funnel, backlog, and workflow-state analysis
Action_By_Role | Text | Yes |  | Controlled role | Action accountability | Subcontractor | Responsibility, ownership, and handoff analysis
Assigned_To_Role | Text | Yes |  | Controlled role | Queue ownership | Architect | Responsibility, ownership, and handoff analysis
Event_Action | Text | No |  | Controlled action | Process mining | Submit | Descriptive segmentation and business context
Revision_Number | Whole number | No |  | Nonnegative | Revision-loop analysis | 0 | Frequency, quality, and process-loop analysis
Decision_Required_Flag | Text | No |  | Yes/No | Decision queue analysis | Yes | Impact-rate and exception analysis
Comment_Category | Text | No |  | Controlled category | Event interpretation | Initial submission | Segmentation and root-cause comparison

## RFI_Change_Links
RFI Change Links - Field Dictionary
Field | Data Type | Nullable | Key / Relationship | Valid Values / Rule | Definition | Example | Primary Analytical Use
Link_ID | Text | No | Primary key | Pattern LNK-##### | Unique relationship identifier | LNK-00001 | Join, filtering, and record traceability
Project_ID | Text | No | FK Projects | Must exist in Projects | Project consistency | PRJ-001 | Join, filtering, and record traceability
RFI_ID | Text | No | FK RFI Log | Must exist in RFI Log | RFI relationship | RFI-00025 | Join, filtering, and record traceability
Change_Order_ID | Text | No | FK Change Orders | Must exist in Change Orders | Change relationship | CO-00004 | Join, filtering, and record traceability
Link_Type | Text | No |  | Controlled link type | Relationship analysis | Supporting Documentation | Segmentation and root-cause comparison
Link_Confidence | Text | No |  | High/Medium/Low | Evidence strength | Medium | Descriptive segmentation and business context
Relationship_Date | Date | No |  | ISO date | Conversion timing | 2024-10-25 | Cycle-time, aging, and sequence analysis
Relationship_Notes_Category | Text | No |  | Controlled notes category | Relationship interpretation | Field condition documented by RFI | Segmentation and root-cause comparison

## Controlled_Values
Controlled Values
Domain | Controlled Value | Applies To | Notes
Project Type | Commercial | Projects | Raw variants are standardized during Process.
Project Type | Heavy Civil & Infrastructure | Projects | Raw variants are standardized during Process.
Project Type | Industrial | Projects | Raw variants are standardized during Process.
Project Type | Institutional | Projects | Raw variants are standardized during Process.
Project Type | Mixed-Use | Projects | Raw variants are standardized during Process.
Project Type | Residential | Projects | Raw variants are standardized during Process.
Delivery Method | Design-Bid-Build | Projects | Raw variants are standardized during Process.
Delivery Method | Design-Build | Projects | Raw variants are standardized during Process.
Delivery Method | CMAR | Projects | Raw variants are standardized during Process.
Delivery Method | IPD | Projects | Raw variants are standardized during Process.
Complexity | Low | Projects | Raw variants are standardized during Process.
Complexity | Moderate | Projects | Raw variants are standardized during Process.
Complexity | High | Projects | Raw variants are standardized during Process.
Complexity | Very High | Projects | Raw variants are standardized during Process.
Digital Coordination | Low | Projects | Raw variants are standardized during Process.
Digital Coordination | Moderate | Projects | Raw variants are standardized during Process.
Digital Coordination | High | Projects | Raw variants are standardized during Process.
Owner Decision Profile | Fast | Projects | Raw variants are standardized during Process.
Owner Decision Profile | Standard | Projects | Raw variants are standardized during Process.
Owner Decision Profile | Slow | Projects | Raw variants are standardized during Process.
RFI Priority | Low | RFI Log | Raw variants are standardized during Process.
RFI Priority | Medium | RFI Log | Raw variants are standardized during Process.
RFI Priority | High | RFI Log | Raw variants are standardized during Process.
RFI Priority | Critical | RFI Log | Raw variants are standardized during Process.
RFI Status | Open | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | In Review | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | Awaiting Designer | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | Awaiting Owner | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | Returned for Clarification | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | Answered | RFI Log / Workflow Events | Raw variants are standardized during Process.
RFI Status | Closed | RFI Log / Workflow Events | Raw variants are standardized during Process.
Discipline | Architectural | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Structural | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Mechanical | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Electrical | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Plumbing | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Civil | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Fire Protection | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Controls | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | General | RFI Log / Change Orders | Raw variants are standardized during Process.
Discipline | Specialty Systems | RFI Log / Change Orders | Raw variants are standardized during Process.
Change Status | Draft | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Submitted | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Under Review | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Pending | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Approved | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Rejected | Change Orders / Workflow Events | Raw variants are standardized during Process.
Change Status | Withdrawn | Change Orders / Workflow Events | Raw variants are standardized during Process.
Link Confidence | High | RFI Change Links | Raw variants are standardized during Process.
Link Confidence | Medium | RFI Change Links | Raw variants are standardized during Process.
Link Confidence | Low | RFI Change Links | Raw variants are standardized during Process.

## Quality_Rules
Process-Phase Data Quality Rules
Rule ID | Category | Table / Relationship | Rule | Failure Treatment
PK-01 | Primary key | Projects | Project_ID nonblank and unique | Remove exact duplicate; quarantine unresolved collision
PK-02 | Primary key | RFI Log | RFI_ID nonblank and unique | Remove exact duplicate; investigate collision
PK-03 | Primary key | Change Orders | Change_Order_ID nonblank and unique | Remove exact duplicate; investigate collision
PK-04 | Primary key | Workflow Events | Event_ID nonblank and unique | Remove exact duplicate; investigate collision
PK-05 | Primary key | RFI Change Links | Link_ID nonblank and unique | Remove exact duplicate; investigate collision
FK-01 | Foreign key | RFI Log → Projects | Project_ID must exist | Quarantine; do not guess parent
FK-02 | Foreign key | Change Orders → Projects | Project_ID must exist | Quarantine; do not guess parent
FK-03 | Foreign key | Workflow Events → Projects | Project_ID must exist | Quarantine; do not guess parent
FK-04 | Foreign key | Links → RFI / Change | Both item IDs must exist | Quarantine invalid link
DT-01 | Date | RFI Log | Submitted ≤ required ≤ final/closed where populated | Repair only from workflow evidence
DT-02 | Date | Change Orders | Identified ≤ submitted ≤ decision/approval | Repair only from workflow evidence
DT-03 | Date | Workflow Events | Sequence and timestamp nondecreasing by item | Repair sequence or quarantine conflicting event
NM-01 | Numeric | All | Counts and impact days nonnegative under documented convention | Correct only with evidence
NM-02 | Numeric | RFI Log | Response quality between 1 and 5 | Correct or quarantine invalid value
ST-01 | Completeness | RFI Log | Answered/Closed requires final response date | Reconstruct from final workflow event
ST-02 | Completeness | Change Orders | Approved requires approval date and approved value | Reconstruct from final workflow evidence
CV-01 | Controlled values | All | Map abbreviations and category variants | Standardize and log mapping
XR-01 | Cross-record | Links | Project IDs agree across project, RFI, and change | Quarantine inconsistent link
XR-02 | Cross-record | Workflow Events | Final event status reconciles to item status | Investigate and document
RC-01 | Reconciliation | All | Raw = clean + duplicate removals + quarantines | Document row reconciliation

## Raw_Profile
Raw Dataset Profile and Known Issues
Table | Raw Rows | Intended Unique | Exact Duplicates | Primary Key
Projects | 92 | 90 | 2 | Project_ID
RFI Log | 3328 | 3320 | 8 | RFI_ID
Change Orders | 1125 | 1120 | 5 | Change_Order_ID
Workflow Events | 11308 | 11298 | 10 | Event_ID
RFI Change Links | 683 | 680 | 3 | Link_ID
Issue Type | Count | Process Treatment
Categorical standardization | 35 | Map variant to controlled value and log.
Exact duplicate | 28 | Remove duplicate and retain one canonical row.
Missing critical value | 10 | Reconstruct only from unambiguous evidence.
Invalid date sequence | 9 | Repair from workflow evidence or quarantine.
Invalid foreign key | 7 | Quarantine; do not guess the parent.
Invalid numeric value | 5 | Correct sign/value only with supporting evidence.
Missing value | 3 | Infer only when supported; otherwise use Unknown.