## Data_KPIs
KPI | Value | Unit
Projects | 90 | count
RFIs | 3318 | count
Average RFI response | 12.21 | days
Median RFI response | 10 | days
RFI on-time rate | 45.68 | percent
Open RFIs | 299 | count
Overdue open RFIs | 295 | count
RFI-to-change conversion | 17.15 | percent
RFI actual cost impact | 29608500 | USD
RFI actual schedule impact | 2572 | days
Change orders | 1119 | count
Approved changes | 706 | count
Approved change value | 204568300 | USD
Pending change exposure | 88104000 | USD absolute
Average approval cycle | 28.91 | days
Median approval cycle | 25 | days
Old pending changes >35 days | 219 | count
Average forecast incorporation lag | 6.58 | days
Linked approved change value | 113056700 | USD unique changes
Median RFI-to-change identification lag | 47 | days

## Data_Health
Workflow Health | Project Count
Red | 29
Yellow | 48
Green | 13

## Data_Top10
Project_ID | Project_Name | Workflow_Risk_Score | Workflow_Health | Avg_Response_Days | Avg_Approval_Cycle_Days | Pending_Exposure_Pct_Budget | Overdue_Open_Rate_Pct | RFI_to_Change_Rate_Pct | Pending_Change_Exposure
PRJ-006 | Summit Corporate Center | 10 | Red | 11.4848 | 32.5 | 0.02658 | 0.175 | 0.15 | 2836000
PRJ-025 | Canyon Transit-Oriented Development | 9 | Red | 17.0323 | 51 | 0.0295 | 0.225 | 0.15 | 1359000
PRJ-075 | Summit Urban Village | 9 | Red | 18.5833 | 43.625 | 0.01403 | 0.1091 | 0.2545 | 3400000
PRJ-051 | Evergreen Apartments | 9 | Red | 21.0962 | 45.8571 | 0.00562 | 0.1613 | 0.1774 | 763000
PRJ-013 | Aspen Civic Complex 2 | 9 | Red | 10.3947 | 29.5714 | 0.00515 | 0.1556 | 0.1556 | 1114000
PRJ-016 | Evergreen Town Center | 8 | Red | 17.025 | 35.6 | 0.01834 | 0.0698 | 0.1628 | 3511000
PRJ-039 | Silver Creek Urban Village 2 | 8 | Red | 12.3077 | 39.3333 | 0.01401 | 0.025 | 0.175 | 1124000
PRJ-019 | Pioneer Research Center | 8 | Red | 14.9423 | 35.8 | 0.0126 | 0.0714 | 0.1607 | 3711000
PRJ-017 | Mountain Gate Transit Center | 8 | Red | 19.0392 | 33.2 | 0.00831 | 0.1639 | 0.1803 | 1146000
PRJ-021 | Desert View Processing Plant | 8 | Red | 18 | 36.4545 | 0.00172 | 0.0294 | 0.2059 | 181000

## Data_RFI
Discipline | RFI_Count | Avg_Response_Days | On_Time_Rate | Overdue_Open | Conversion_Rate | Cost_Impact | Schedule_Days
Specialty Systems | 231 | 13.64 | 0.412 | 20 | 0.147 | 1872400 | 188
Mechanical | 480 | 13.43 | 0.387 | 40 | 0.192 | 4939500 | 365
Electrical | 518 | 12.98 | 0.425 | 50 | 0.178 | 5146900 | 436
Structural | 413 | 12.95 | 0.411 | 43 | 0.174 | 2972300 | 302
Fire Protection | 181 | 12.41 | 0.434 | 8 | 0.166 | 2022800 | 152
Civil | 285 | 12.38 | 0.449 | 21 | 0.175 | 2363600 | 219
Controls | 157 | 12.18 | 0.49 | 10 | 0.191 | 1821600 | 158
Plumbing | 283 | 11.18 | 0.486 | 28 | 0.134 | 2997100 | 229
Architectural | 495 | 10.89 | 0.51 | 53 | 0.168 | 3309000 | 316
General | 275 | 9.46 | 0.623 | 22 | 0.175 | 2163300 | 207

## Data_RFI_Type
RFI_Type | RFI_Count | Avg_Response_Days | On_Time_Rate | Conversion_Rate | Cost_Impact | Schedule_Days
Coordination Conflict | 757 | 12.32 | 0.469 | 0.189 | 8225100 | 533
Design Clarification | 872 | 12.21 | 0.473 | 0.133 | 6777000 | 449
Missing Information | 478 | 12.25 | 0.429 | 0.18 | 4057500 | 525
Constructability | 404 | 11.76 | 0.459 | 0.163 | 3651100 | 269
Field Condition | 386 | 12.12 | 0.44 | 0.21 | 3559900 | 494
Substitution Request | 259 | 12.65 | 0.422 | 0.197 | 2436100 | 211
Code Compliance | 162 | 12.31 | 0.483 | 0.16 | 901800 | 91

## Data_Change
Change_Category | Change_Count | Approved_Count | Pending_Count | Approved_Value | Pending_Exposure | Avg_Approval_Days | Approved_Schedule_Days | Linked_Change_Count | Avg_Forecast_Lag_Days
Owner-Directed Change | 198 | 126 | 41 | 44093100 | 22849000 | 32.33 | 454 | 46 | 7.28
Design Error or Omission | 197 | 118 | 41 | 40302400 | 14907000 | 32.92 | 216 | 135 | 6.32
Unforeseen Condition | 168 | 108 | 29 | 39882000 | 17020000 | 28.41 | 275 | 114 | 6.9
Code or Regulatory Requirement | 78 | 54 | 10 | 16442100 | 6094000 | 31.96 | 66 | 37 | 6.32
Substitution | 94 | 60 | 22 | 14284000 | 6963000 | 25.77 | 81 | 51 | 6.47
Value Engineering | 93 | 62 | 19 | 13922100 | 5604000 | 24.6 | 149 | 37 | 5.55
Schedule Acceleration | 78 | 49 | 15 | 13904000 | 2254000 | 30.04 | 119 | 41 | 5.72
Quantity Variation | 106 | 65 | 19 | 11806400 | 6831000 | 23.74 | 119 | 55 | 7.9
Scope Clarification | 107 | 64 | 25 | 9932200 | 5582000 | 24.53 | 59 | 61 | 5.9

## Data_Workflow
Item_Type | To_Status | Assigned_To_Role | Event_Count | Avg_Stage_Days | Total_Stage_Days | Handoff_Count | Revision_Loop_Count
Change Order | Approved | Project Manager | 706 | 20.31 | 14335.35 | 706 | 0
RFI | Closed | Subcontractor | 948 | 9.93 | 9411.6 | 756 | 0
RFI | Closed | General Contractor | 925 | 9.57 | 8854.16 | 696 | 0
Change Order | Returned for Revision | Cost Manager | 512 | 16.7 | 8552.62 | 511 | 512
Change Order | Submitted | Owner Representative | 1117 | 7.03 | 7850.68 | 1117 | 0
RFI | Returned for Clarification | General Contractor | 344 | 11.95 | 4109.42 | 344 | 344
RFI | Returned for Clarification | Subcontractor | 308 | 10.86 | 3345.12 | 308 | 308
RFI | Answered | General Contractor | 350 | 9.48 | 3319.07 | 267 | 0
Change Order | Rejected | Project Manager | 113 | 28.89 | 3264.7 | 113 | 0
RFI | Answered | Subcontractor | 337 | 9.64 | 3247.93 | 257 | 0
RFI | Closed | Construction Manager | 332 | 9.75 | 3235.64 | 229 | 0
Change Order | Pending | Project Manager | 220 | 14.03 | 3086.36 | 220 | 0
Change Order | Withdrawn | Project Manager | 79 | 22.33 | 1763.96 | 79 | 0
RFI | Returned for Clarification | Construction Manager | 134 | 11.01 | 1475.78 | 119 | 134
RFI | Answered | Construction Manager | 127 | 9.64 | 1224.9 | 81 | 0
RFI | In Review | Engineer | 54 | 7.41 | 400.18 | 4 | 0
RFI | Awaiting Designer | Engineer | 39 | 7.69 | 299.81 | 6 | 0
RFI | Open | Engineer | 30 | 7.41 | 222.43 | 7 | 0
RFI | Returned for Clarification | Engineer | 24 | 8.06 | 193.49 | 3 | 24
RFI | Awaiting Owner | Engineer | 28 | 5.93 | 166.17 | 7 | 0
RFI | Awaiting Owner | Architect | 13 | 8.79 | 114.27 | 2 | 0
RFI | In Review | Architect | 16 | 7.1 | 113.66 | 2 | 0
RFI | Awaiting Designer | Owner Representative | 11 | 6.64 | 73.01 | 2 | 0

## Data_Segments
Segment_Type | Segment | RFI_Count | Avg_RFI_Response_Days | On_Time_Rate | Change_Count | Avg_Approval_Cycle_Days | Pending_Exposure
Owner Decision Profile | Fast | 597 | 10.4 | 0.528 | 197 | 24.36 | 12516000
Owner Decision Profile | Standard | 1905 | 11.01 | 0.515 | 623 | 26.01 | 52494000
Owner Decision Profile | Slow | 816 | 16.45 | 0.263 | 299 | 37.98 | 23094000
Digital Coordination Level | High | 881 | 9.55 | 0.62 | 304 | 26.39 | 25448200
Digital Coordination Level | Moderate | 1675 | 12.63 | 0.425 | 567 | 30.02 | 48307800
Digital Coordination Level | Low | 762 | 14.39 | 0.336 | 248 | 29.29 | 14348000

## Executive_Dashboard
Construction Change Order and RFI Analytics
Executive portfolio view ¦ Decision speed, commercial exposure, workflow health, and management priorities. All records are synthetic.
90 |  |  | 3318 |  |  | 12.21 | 45.68%
Projects |  |  | RFIs |  |  | Avg RFI Response | RFI On-Time
204568300 |  |  | 88104000 |  |  | 28.91 | 17.15%
Approved Change Value |  |  | Pending Exposure |  |  | Avg Approval Cycle | RFI-to-Change
Workflow Health | Projects | [5 empty] | Change Category | Approved Value | Pending Exposure
Red | 29 | [5 empty] | Owner-Directed Change | 44093100 | 22849000
Yellow | 48 | [5 empty] | Design Error or Omission | 40302400 | 14907000
Green | 13 | [5 empty] | Unforeseen Condition | 39882000 | 17020000
[7 empty] | Code or Regulatory Requirement | 16442100 | 6094000
[7 empty] | Substitution | 14284000 | 6963000
Key Findings
1 | Cross-process speed | Project-average RFI response and change approval cycle have the strongest tested association: Pearson r = 0.817; R² = 0.668.
2 | Decision profile | Slow owner-decision projects averaged 16.45 RFI-response days, 26.3% on-time RFI performance, and 37.98 change-approval days.
3 | Digital coordination | High digital-coordination projects averaged 9.55 response days and 62.0% on-time performance.
4 | RFI impact driver | Coordination Conflict RFIs generated the greatest actual cost impact: $8.23M and 533 schedule-impact days.
5 | Commercial concentration | Owner-directed, design error/omission, and unforeseen-condition changes generated $124.28M in approved value.
Project ID | Project | Risk Score | Health | Avg RFI Days | Avg Approval Days | Pending / Budget
PRJ-006 | Summit Corporate Center | 10 | Red | 11.4848 | 32.5 | 2.658%
PRJ-025 | Canyon Transit-Oriented Development | 9 | Red | 17.0323 | 51 | 2.95%
PRJ-075 | Summit Urban Village | 9 | Red | 18.5833 | 43.625 | 1.403%
PRJ-051 | Evergreen Apartments | 9 | Red | 21.0962 | 45.8571 | 0.562%
PRJ-013 | Aspen Civic Complex 2 | 9 | Red | 10.3947 | 29.5714 | 0.515%

## Operational_Dashboard
Operational Workflow Dashboard
RFI performance, root-cause impact, change approval, and portfolio workflow interpretation.
Discipline | RFIs | Avg Response | On-Time | Overdue Open | RFI-to-Change |  | Discipline | Avg Response
Specialty Systems | 231 | 13.64 | 41.2% | 20 | 14.7% |  | Specialty Systems | 13.64
Mechanical | 480 | 13.43 | 38.7% | 40 | 19.2% |  | Mechanical | 13.43
Electrical | 518 | 12.98 | 42.5% | 50 | 17.8% |  | Electrical | 12.98
Structural | 413 | 12.95 | 41.1% | 43 | 17.4% |  | Structural | 12.95
Fire Protection | 181 | 12.41 | 43.4% | 8 | 16.6% |  | Fire Protection | 12.41
Civil | 285 | 12.38 | 44.9% | 21 | 17.5% |  | Civil | 12.38
Controls | 157 | 12.18 | 49% | 10 | 19.1% |  | Controls | 12.18
Plumbing | 283 | 11.18 | 48.6% | 28 | 13.4% |  | Plumbing | 11.18
Architectural | 495 | 10.89 | 51% | 53 | 16.8% |  | Architectural | 10.89
General | 275 | 9.46 | 62.3% | 22 | 17.5% |  | General | 9.46
RFI Type | RFIs | Cost Impact | Schedule Days | Conversion Rate |  |  | RFI Type | Cost Impact
Coordination Conflict | 757 | 8225100 | 533 | 18.9% |  |  | Coordination Conflict | 8225100
Design Clarification | 872 | 6777000 | 449 | 13.3% |  |  | Design Clarification | 6777000
Missing Information | 478 | 4057500 | 525 | 18% |  |  | Missing Information | 4057500
Constructability | 404 | 3651100 | 269 | 16.3% |  |  | Constructability | 3651100
Field Condition | 386 | 3559900 | 494 | 21% |  |  | Field Condition | 3559900
Substitution Request | 259 | 2436100 | 211 | 19.7% |  |  | Substitution Request | 2436100
Code Compliance | 162 | 901800 | 91 | 16% |  |  | Code Compliance | 901800
Change Category | Count | Approved | Pending | Approved Value | Pending Exposure | Avg Approval | Change Category | Approved Value | Pending Exposure
Owner-Directed Change | 198 | 126 | 41 | 44093100 | 22849000 | 32.33 | Owner-Directed Change | 44093100 | 22849000
Design Error or Omission | 197 | 118 | 41 | 40302400 | 14907000 | 32.92 | Design Error or Omission | 40302400 | 14907000
Unforeseen Condition | 168 | 108 | 29 | 39882000 | 17020000 | 28.41 | Unforeseen Condition | 39882000 | 17020000
Code or Regulatory Requirement | 78 | 54 | 10 | 16442100 | 6094000 | 31.96 | Code or Regulatory Requirement | 16442100 | 6094000
Substitution | 94 | 60 | 22 | 14284000 | 6963000 | 25.77 | Substitution | 14284000 | 6963000
Value Engineering | 93 | 62 | 19 | 13922100 | 5604000 | 24.6 | Value Engineering | 13922100 | 5604000
Schedule Acceleration | 78 | 49 | 15 | 13904000 | 2254000 | 30.04 | Schedule Acceleration | 13904000 | 2254000
Quantity Variation | 106 | 65 | 19 | 11806400 | 6831000 | 23.74 | Quantity Variation | 11806400 | 6831000
Scope Clarification | 107 | 64 | 25 | 9932200 | 5582000 | 24.53 | Scope Clarification | 9932200 | 5582000
Operational interpretation: response-time and approval-cycle performance should be reviewed together. The strongest project-level relationship indicates that decision and coordination conditions affect both workflows.

## Project_Priority
Top 10 Project Workflow Priorities
Management-priority list based on transparent cumulative triggers. Review project context before assigning corrective action.
Rank | Project ID | Project Name | Risk Score | Health | Avg RFI Days | Avg Approval Days | Pending / Budget | Overdue Open Rate | RFI-to-Change | Pending Exposure
1 | PRJ-006 | Summit Corporate Center | 10 | Red | 11.4848 | 32.5 | 2.658% | 17.5% | 15% | 2836000
2 | PRJ-025 | Canyon Transit-Oriented Development | 9 | Red | 17.0323 | 51 | 2.95% | 22.5% | 15% | 1359000
3 | PRJ-075 | Summit Urban Village | 9 | Red | 18.5833 | 43.625 | 1.403% | 10.91% | 25.45% | 3400000
4 | PRJ-051 | Evergreen Apartments | 9 | Red | 21.0962 | 45.8571 | 0.562% | 16.13% | 17.74% | 763000
5 | PRJ-013 | Aspen Civic Complex 2 | 9 | Red | 10.3947 | 29.5714 | 0.515% | 15.56% | 15.56% | 1114000
6 | PRJ-016 | Evergreen Town Center | 8 | Red | 17.025 | 35.6 | 1.834% | 6.98% | 16.28% | 3511000
7 | PRJ-039 | Silver Creek Urban Village 2 | 8 | Red | 12.3077 | 39.3333 | 1.401% | 2.5% | 17.5% | 1124000
8 | PRJ-019 | Pioneer Research Center | 8 | Red | 14.9423 | 35.8 | 1.26% | 7.14% | 16.07% | 3711000
9 | PRJ-017 | Mountain Gate Transit Center | 8 | Red | 19.0392 | 33.2 | 0.831% | 16.39% | 18.03% | 1146000
10 | PRJ-021 | Desert View Processing Plant | 8 | Red | 18 | 36.4545 | 0.172% | 2.94% | 20.59% | 181000
Recommended review sequence: validate backlog and owner decisions; resolve High/Critical overdue RFIs; assign owners and due dates to old pending changes; incorporate approved changes into forecasts; then address repeated revision loops.

## Sources
Sources, Methodology, and Disclosure
Project source files, lifecycle terminology references, and public-use disclosure.
Source Type | Source | Location / URL | Use
Project data | Validated SQLite database | data/processed/construction_change_order_rfi_analytics.sqlite | Primary analytical source
Project data | Analysis tables | analysis/tables/*.csv | Dashboard inputs
Methodology | IBM CRISP-DM overview | https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=dm-crisp-help-overview | Lifecycle terminology
Methodology | ASQ DMAIC | https://asq.org/quality-resources/dmaic | Process-improvement terminology
Methodology | Microsoft Data Science Lifecycle | https://learn.microsoft.com/en-us/shows/dev-intro-to-data-science/what-is-the-data-science-lifecycle-2-of-28 | Modeling terminology
Methodology | PMI Process Groups | https://www.pmi.org/standards/process-groups | Project-governance terminology
Synthetic-data disclosure: All project names, organizations, people, budgets, schedules, changes, RFIs, and performance records are fictional and were created for education, portfolio demonstration, and analytical-methodology development. They do not represent actual In Project LLC clients or confidential construction records.

## Workflow_Analysis
Workflow Bottlenecks and Operating Segments
Stage-duration, handoff, revision-loop, owner-decision, and digital-coordination analysis.
Item Type | Status | Assigned Role | Events | Avg Stage Days | Total Stage Days | Handoffs | Revision Loops | Stage | Total Stage Days
Change Order | Approved | Project Manager | 706 | 20.31 | 14335.35 | 706 | 0 | Approved ¦ Project Manager | 14335.35
RFI | Closed | Subcontractor | 948 | 9.93 | 9411.6 | 756 | 0 | Closed ¦ Subcontractor | 9411.6
RFI | Closed | General Contractor | 925 | 9.57 | 8854.16 | 696 | 0 | Closed ¦ General Contractor | 8854.16
Change Order | Returned for Revision | Cost Manager | 512 | 16.7 | 8552.62 | 511 | 512 | Returned for Revision ¦ Cost Manager | 8552.62
Change Order | Submitted | Owner Representative | 1117 | 7.03 | 7850.68 | 1117 | 0 | Submitted ¦ Owner Representative | 7850.68
RFI | Returned for Clarification | General Contractor | 344 | 11.95 | 4109.42 | 344 | 344 | Returned for Clarification ¦ General Contractor | 4109.42
RFI | Returned for Clarification | Subcontractor | 308 | 10.86 | 3345.12 | 308 | 308 | Returned for Clarification ¦ Subcontractor | 3345.12
RFI | Answered | General Contractor | 350 | 9.48 | 3319.07 | 267 | 0 | Answered ¦ General Contractor | 3319.07
Change Order | Rejected | Project Manager | 113 | 28.89 | 3264.7 | 113 | 0 | Rejected ¦ Project Manager | 3264.7
RFI | Answered | Subcontractor | 337 | 9.64 | 3247.93 | 257 | 0 | Answered ¦ Subcontractor | 3247.93
RFI | Closed | Construction Manager | 332 | 9.75 | 3235.64 | 229 | 0
Change Order | Pending | Project Manager | 220 | 14.03 | 3086.36 | 220 | 0
Change Order | Withdrawn | Project Manager | 79 | 22.33 | 1763.96 | 79 | 0
RFI | Returned for Clarification | Construction Manager | 134 | 11.01 | 1475.78 | 119 | 134
RFI | Answered | Construction Manager | 127 | 9.64 | 1224.9 | 81 | 0
Segment Type | Segment | RFIs | Avg RFI Days | On-Time | Changes | Avg Approval | Pending Exposure | Owner Profile | Avg Approval
Owner Decision Profile | Fast | 597 | 10.4 | 52.8% | 197 | 24.36 | 12516000 | Fast | 24.36
Owner Decision Profile | Standard | 1905 | 11.01 | 51.5% | 623 | 26.01 | 52494000 | Standard | 26.01
Owner Decision Profile | Slow | 816 | 16.45 | 26.3% | 299 | 37.98 | 23094000 | Slow | 37.98
Digital Coordination Level | High | 881 | 9.55 | 62% | 304 | 26.39 | 25448200
Digital Coordination Level | Moderate | 1675 | 12.63 | 42.5% | 567 | 30.02 | 48307800
Digital Coordination Level | Low | 762 | 14.39 | 33.6% | 248 | 29.29 | 14348000
Management implication: approval and response delays are concentrated in review and revision loops. The operating-segment comparison supports targeted governance for Slow decision profiles and Low digital-coordination projects.